## OPEN
NAME OF GROUP: LONDON Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Date action started | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-07 | Social Care Placements | Audit number of Universities in London offering nursing and NA, number of social care placements per uni | Data to identify: number universities of nursing, total students, total placements, number of SC placements. Potentially getting the data from NHS Workforce Training and Education | Pam Hodge | Jan-26 | Ongoing action. Update to be provided at the next meeting. Pam will invite Louise to attend the Pan London Practice Learning Group.
2025-01-07 | Virtual Wards and Delegated tasks | Create a list of the delegated tasks currently happing in social care providers. | Aiming to get Representatives from Independent providers to liaise with insurers to ensure the nursing activities delegated to ASC providers are correctly insured. Ongoing actions. Care England is leading on this contact between providers and Insurers to clarify the topic. This is a long term action. Round table organised by Care England in November. | Louise, Richard Ayres | Jan-26 | Richard to provide an update from an insurance point of view at the next meeting.
2025-04-04 | IV treatments in ASC | Create a list of requirements to be able to administer IV treatments by ASC providers | Create a separate group that will look into the implementation of IV administration passport in social care. Essential to involve front line social care providers. | Louise Keane, Anna Lynch, Anne Middleton, Lauren Hague (Care England), Pauline Fahy, Social Care providers | Jan-26 | Louise is continuing to persevere to find management support to implement this project. Members of the working group: Mirko (Majesticare), Maggie (Cavendish) and Karen Davies (HCOne), Beatrice (Barchester), Samsam (Nightingale Hammerson)
2025-01-07 | London Ambulance Service (LAS) | LAS data on care home incidents to be worked and shared with the council. Invite LAS leads for care homes to attend next meeting | Meet to create an easy to digest data to be presented at the next meeting. | Nunot Santos Lopes / Louise Keane | Jan-26 | 14Oct25 Nuno in contact with the LAS CEO Jason Killens and awaiting an update on when the data will be available. 15Jul25 Once there is someone within LAS able to collate the data it will be presented at the Council.
2025-01-07 | Competencies Passport in ASC | Update on the progress for the creation of this document | Funding secured from the FoNS to employ someone to work on this project and produce the national document. | Louise Keane | Jan-26 | Aiming to publish in November the first version. Louise is going to provide an update at the next meeting.
2025-10-14 | Competency Framework Review | Send the draft clinical competencies for adult social care nursing to interested Council members for review and feedback, ensuring responses are received within tight deadline | Please contact Louise directly (louise.london@scnac.co.uk) but if you have time to review within a short period of time | All / Louise | ASAP
2025-10-14 | Research | Share the studies that are currently recruiting in ASC. | Share a list of the studies, together with the link to the website Be Part of Research | Dawn Beaumont | Oct-25 | Link included on the Updates and Information tab AND in the Notes document
2025-10-14 | Research | Add a member of the North London NIHR Research Deliver network to the Council. | Identify the right person within the North London NIHR RRDN to be a council member | Nuno | Jan-26
2025-10-14 | NMC | Share the slides of the NMC Employer Link Service Advisor service | Share the slides | Tawanda Bvumburai | Oct-25 | Sonia requested by email
2025-10-14 | University Engagement for Student Placements | Send over the slides from Lucy Gillespie regarding the survey results on student placements in adult social care to all council members |  | Louise | ASAP
2025-10-14 | University Engagement for Student Placements | Contact the Chair and Co-Chair of the Pan London Practise Learning Group to request a slot for Louise or Joanna to present at the next meeting |  | Pam Hodge | ASAP
2025-10-14 | Induction in Adult Social Care Resource Development | Coordinate with Dudley and Jacqueline to develop and review a draft of the induction resource for adult social care and provide and update at the next meeting |  | Louise / Dudley / Jacqueline | At Next Meeting
2025-10-14 | Leadership Programme Survey | Notify Sonia when the RCN Leadership Programme Survey for Adult Social Care Nurses goes live so that it can be shared with the council. |  | Millie | When Available
2025-07-15 | LD or Mental Health Nurse Vacancies | If anyone has or knows of any LD or Mental Health Nurse vacancies that would suit nurses due to qualify in September, please let Louise know and she will put you in touch with the relevant contact. | Please note that many of these nurses are on student visas so would need to be an A-rated provider to take them on. | All / Louise Keane | As available | 14Oct25 Joanna Grant to put Louise Keane in touch with people on her team for LD and Mental Health

## Complete
NAME OF GROUP: LONDON Region Social Care Nursing Advisory Councils (SCNACs) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-07 | Social Care Placements | Audit number of Universities in London offering nursing and NA, number of social care placements per uni | Data to identify: number universities of nursing, total students, total placements, number of SC placements. Potentially getting the data from NHS Workforce Training and Education | Pam Hodge | Oct-25 | 15Jul25 Pam attended the Pan London Practise Learning Group Social Care Meeting. Lots of interest in increasing placements through different strategies. Next meeting will be in the autumn term so she will report at the next meeting. Louise is waiting for the results of the Council of Deans survey from Skills for Care and will report on this also a the next meeting. | Action superceded at Oct-25 Meeting
2025-01-07 | Virtual Wards and Delegated tasks | Create a list of the delegated tasks currently happening in social care providers. | Aiming to get Representatives from Independent providers to liaise with insurers to ensure the nursing activities delegated to ASC providers are correctly insured. | Louise Keane / Richard Ayres | Oct-25 | 15Jul25 Ongoing actions. Care England is leading on this contact between providers and insurers to clarify the topic. This is a long term action. Present an update in October | Action superceded at Oct-25 Meeting
2025-04-04 | IV treatments in ASC | Create a list of requirements to be able to administer IV treatments by ASC providers | Create a separate group that will look into the implementation of IV administration passport in social care. Essential to involve front line social care providers | Louise Keane / Nuno Santos Lopes / Anna Lynch / Anne Middleton / Lauren Hague / Pauline Fahy / Social Care Providers | Oct-25 | 15Jul25 Awaiting feedback from the NHS on the potential implementation of the programme. Members of the working group: Mirko (Majesticare), Maggie (Cavendish) and Karen Davies (HCOne), Beatrice (Barchester), Samsam (Nightingale Hammerson) | Action superceded at Oct-25 Meeting
2025-01-07 | Induction on Adult Social Care | Establish the knowledge NHS and LA staff need to have about ASC | Present update on the knowledge required at the next meeting and decide the way forward | Louise Keane / Maggie Candy / Dudley Sawyer | Jan26 | 15Jul25 British Film Foundation have gone quiet but Care Magazine might be interested in supporting on this. Will develop and bring it back for SCNAC to look at | Action superceded at Oct-25 Meeting
2025-07-15 | New NMC Employer Link Service Advisor | Tawanda to provide details of her new role and we will put this on the London SCNAC webpage. |  | Tawanda Bvumburai | ASAP |  | 2025-10-14
2025-07-15 | Social Care Leadership Course | Send out flyer for the leadership course for nurses in Adult Social Care and provide an update on development at the next meeting |  | Millie Simms / Louise Keane | Jul-25 / Oct-25 |  | 2025-10-14
2025-07-15 | New London SCNAC Co-Chair | Advert to be published for expressions of interest to chair the London SCNAC | The Outstanding Society will share the advert and manage the process | Sonia / The OS | Oct-25 |  | 2025-09-30
2025-07-15 | Blog on IV Administration in the Community | Louise to send article to Sonia for dissemination to council members |  | Louise Keane / Sonia | Jul-25
2025-04-04 | Updates | Share with the members an update on the University of Salford research events, Care Show London and Care Home Referral Guidance | Share Slides | Sonia | Apr-25 |  | 2025-04-07
2025-01-07 | Population Health Management System Dashboard | Identify what is the relevant data for the ASC sector from the Population Health Management Dashboard | Identify the relevant data that can be shared with the council to create discussions on how ASC nursing can help with supporting the population. | Vi Thomas / Nuno / Louise Keane | Jun 25 | 15Jul25 It was decided to close this action point as to date it has not been possible to provide the data so unlikely to be possible in the future.
2025-01-07 | Population Health Management System Dashboard | Identify what is the relevant data for the ASC sector from the Population Health Management Dashboard | Nuno and Karen to identify the relevant data that can be shared with the council to create discussions on how ASC nursing can help with supporting the population. | Karen Bonner / Nuno | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | Social Care Placements | Audit number of Universities in London offering nursing and NA, number of social care placements per uni | Data to identify: number universities of nursing, total students, total placements, number of SC placements. Potentially getting the data from NHS Workforce Training and Education | Vi Thomas / Karen Bonner | Mar-25 | So far we have got data from the Middlesex University. Action updated following 04Apr25 meeting
2025-01-07 | NHS Training Induction on Adult Social Care | Establish the knowledge requirements NHS and LA staff need to understand more about ASC, including the differences between care homes, nursing homes, mental health and other relevant areas. | Present these requirements at the next meeting and decide the way forward. | Louise K / Dudley / Pauline S / Jane W / Maggie C | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | Virtual Wards and Delegated tasks | Compile a list of the delegated tasks currently happening in social care providers. | Aiming to get representatives from independent providers to work with insurers to ensure the nursing activities delegated to ASC providers are correctly insured. | Louise K / Richard A / Peter W | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | IV treatments in ASC | Create a list of requirements for ASC providers to be able to administer IV treatments. | Share list of requirements with the group at the next meeting, in liaison with Capital Nursing. | Louise K | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | London Ambulance Service (LAS) | LAS data on care home incidents to be worked and shared with the council. Invite LAS leads for care homes to attend next meeting | Aiming to get a general understanding of the key highlights and learnings that we can get from the data | Nuno / Louise K / LAS | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | SCNACs Update Meeting - Friday 17th January 2025 from 14:30-15:30 | Book your free place now at this meeting | https://www.eventbrite.co.uk/e/social-care-nursing-advisory-councils-where-are-we-now-tickets-1113668224639?aff=oddtdtcreator | SCNACs | 2025-01-17 |  | 2025-01-17
2025-01-07 | LLW Meeting Notes | Peter to forward any relevant infromation from the recent LLW meeting once the notes are received |  | Peter W | Once notes received |  | 2025-01-08
2024-06-25 | NHS England Workforce Training and Education (WTE) | Talk to WTE about their plans to implement the long-term workforce plan, understanding how is social care involved and share with the Council |  | Jane Clegg/ Pam H / Nuno | 2024-07-31 | Audit - Pam to help with re. unis. Nuno to help Superseded with action points from 07Jan25 meeting
2024-06-25 | Skill Needs for the Social Care Sector | Explore with the NHS Workforce Training and Education whether they have data on the skill needs for the social care sector |  | Jane Clegg | 2024-11-15 | 25-Sep: Jane needs to chase this up. Superseded with action points from 07Jan25 meeting
2025-01-07 | Population Health Management System Dashboard | Identify relevant data available in the DHSC about Adult Social Care | Nuno to meet with DHSC to look into the relevant data available to guide council discussions | Deborah Sturdy/ Nuno | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | Skill Needs for the Social Care Sector | Continue to work on the steering group to develop the minimum skills standards for nurses and nursing associates in social care (care homes, domiciliary care, LD, Mental Health) and update at the next meeting. | Work to create the skills and competences required for nursing in social care with the colleague in the South East SCNAC. Involve Benedicta (SEL ICB), Mirko (Majesticare), Beatrice (Barchester), Laura (Skills for Care), Richard (Care England), Millie (RCN), Lizzie (SEL ICB) | Nuno / Louise K | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | Social Care Placements | Analyse the current capacity from care providers to welcome Nursing students, including data if possible. | Present at the next council meeting the outcomes. | Louise K / Pam H / Richard A / Nuno | Mar-25 | Action updated following 04Apr25 meeting
2025-01-07 | Social Care Placements | Skills for Care are developing a strategy to ensure SC is a placement of choice for nursing students and nursing associates. Laura will keep the council updated. | See updates and information tab for Skills for Care and RCN resources shared in the chat | Laura | As available | Action updated following 04Apr25 meeting
2025-01-07 | Virtual Wards | Louise to attend Virtual Wards steering group | Feedback on the main issues facing the ASC and NHS to make it effective. | Louise K | Ongoing | Action updated following 04Apr25 meeting
2024-09-25 | Skill Needs for the Social Care Sector | Explore with the NHS Workforce Training and Education whether they have data on the skill needs for the social care sector |  | Karen Bonner | 2025-04-01 | Karen Bonner has taken over the position from Jane Clegg and will pick this up.
2024-09-25 | Population Health Management System Dashboard | Share the Population Health Management System Dashboard for each ICB with the council members | To help identify the changing needs of the population | Jane Clegg | 2024-09-24 | Information already shared Health Profile for London 2021 (https://fingertips.phe.org.uk/static-reports/health-profile-for-england/regional-profile-london.html). Pending now to discuss with Louise about a potential presentation at the next Council from OHID
2024-09-25 | London Living Wage | Peter Webb to share the presentation from the LLW group |  | Peter Webb | 2024-10-24 | Presentation shared and will be discussed in future meeting. | 2024-12-23
2024-09-25 | CQC | Invite a CQC representative to the council |  | Nuno | 2024-12-24 | Will be joining from the next quarterly meeting - Apr25 | 2024-12-20
2024-09-25 | Research | Consult with NIHR to identify whether there is a place where all the social care research studies happening in London are stored. |  | Dawn / Nuno | 2024-11-24 | The following 2 websites are publicly available and anyone can access and register to get updates. https://bepartofresearch.nihr.ac.uk/ https://www.joindementiaresearch.nihr.ac.uk/ NIHR has got a system called Open Data Platform (ODP). As Social Care has now been named as a dedicated speciality, we will be able to filter the data specifically for Social Care studies which will make things much easier - this filter will go live on 23-Oct-24. There are a lot of other filters we can apply to the data depending on what you would like to know. We will definitely be able to see which Social Care studies are open across London, how many people are taking part in those studies and exactly where the studies are open (e.g. which particular care homes.) | Filter to go live 23Oct24
2024-06-25 | Pay, terms and conditions | Share information about the T&Cs comparing social care and NHS with the council. |  | Nuno / Millie / Lauren | ASAP for Peter sharing slides | 25-Sep-24: Lauren shared a report. Unfair to care 2024. Page 22 - Gap is 10%. Gap can be up to 55% when pension is added. This can be a reason in social care sector that providers might struggle with recruitmement. Has been raised with Primary Care but not Adult Social Care. We are trying to show adult social care can be part of student nurses' journey. Louise has raised with RCN. Jane - will reflect this conversation. Peter - Meeting with London Living Wage group recently. There have been stats rolled out. When he gets slides he will share these. Agenda topic for future meeting | 2024-12-23
2024-06-25 | Population Health Management System Dashboard | Share the Population Health Management System Dashboard for each ICB with the council members | To help identify the changing needs of the population | Chief Nurse for each ICB | 2024-07-31 | 25-Sep: Jane Clegg said work in progress - continuing to work on
2024-06-25 | Changes in the Population's Needs | Explore with the QNI (Queens Nursing Institute) whether they have got any London/National data that describes the changes in the populations’ needs. | Also to help identify the changing needs of the population | Jane Clegg | 2024-07-31 | 25-Sep: Jane to have conversation with OHIP re. data - she is happy to pick up on that (Kevin Fenton Regional Director)
2024-06-25 | Maps of Needed Skills | Share the map out of the skills needed in North Central London |  | Louise K | 2024-10-30 | 25-Sep: Powerpoint presentation went out on invite. Louise Keane went out to nursing homes last year, and other settings to see where they are with training and what they need. Saw different levels of support. They are out again doing second nursing survey. Should have data soon to see difference. Level of concern with revalidating with NMC - Not being able to access data. On the back of work they did with North Central London - work on sessions, have sent Louise an email to say they feel more confident with revalidation. | 2024-09-25
2024-06-25 | Curriculum for both Nursing and Nursing Associates | Share the curriculums of Nursing and Nursing Associate Studies with the council |  | Pam H | 2024-07-31 | 25th Sep: Shared curriculum for overview of Middlesex. If anyone has specific questions she can be available for this. Re sub committee - speaking to student nurses, this would be an incentive to see their structure of possible career progression. | 2024-09-25
2024-06-25 | Terms of Reference (ToR) | Agree the ToR and upload onto webpage | If you have any comments or concerns, please email them across | All | 2024-07-12 | No Concerns received | 2024-07-12
2024-06-25 | Skills for Care Data | Will see what data is available to be shared on needs but more likely to be around workforce and vacancies |  | Laura Anthony | 2024-07-31 | If you go to: https://www.skillsforcare.org.uk/Adult-Social-Care-Workforce-Data/Workforce-intelligence/publications/regional-information/My-region.aspx and then select London. For each section - recruitment & retention, demographics, etc. there's the option at the top to select the Registered Nurse role. Anything you can't find that would be helpful just let me know and I can speak to our Analysis team | 2024-06-25

## Updates and Information
NAME OF GROUP: LONDON Region Social Care Nursing Advisory Councils (SCNACs) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-10-14 | Skills for Care Student Nurse and Early Career Network | Shared in the chat by Laura Anthony: | https://www.councilofdeans.org.uk/social-care-network-for-students-and-early-career-nurses/ | Skills for Care
2025-10-14 | Skills for Care Global Majority Network | Shared in the chat by Laura Anthony: | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Join-the-nursing-community.aspx | Skills for Care
2025-10-14 | NHS England, Student Hub - Workforce, Training and Education | Shared in the chat by Jacqueline Robinson-Rouse: | https://www.hee.nhs.uk/our-work/student-hub-1 | NHS England
2025-10-14 | NHS England - Understanding the Role of Nursing in Social Care | Shared in the chat by Jacqueline Robinson-Rouse: | https://www.hee.nhs.uk/our-work/nursing-social-care/understanding-role-nursing-social-care | NHS England
2025-10-14 | Skills for Care Social Care Nursing Placement Strategy | Shared in the chat by Laura Anthony and launched in July 2025: | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Pre-registration/Student-nurses-and-nursing-associates.aspx | Skills for Care | 2025-11-11
2025-10-14 | Be Part of Research | Shared in the chat by Alison Anstead | https://bepartofresearch.nihr.ac.uk/ | NIHR
2025-10-14 | reach by Nightingale Hammerson - Care Home Research Forum | Shared in the chat by Clemench Muchingaguyo | https://nightingalehammerson.org/reach/research/chrf-2025/ | Nightingale Hammerson | 2025-11-06
2025-10-14 | Shining a Light on Registered Nurses in Learning Disability Working in Social Care Webinar | Shared in the chat by Joanna Grant: | https://www.rcn.org.uk/news-and-events/events/Out-of-the-shadows-Shining-a-light-on-registered-nurses-in-learning-disability-131125 | RCN | 2025-11-13
2025-10-14 | Guardian Newspaper Article | Shared in the chat by Peter Webb: | https://www.theguardian.com/society/2025/oct/14/britain-toxic-race-debate-threaten-overseas-care-workers |  | For Reference
2025-07-15 | Changes in Immigration Rules | Vinice (Vi) Thomas, Director of Nursing and Quality for NHSE London Region she has been made aware that a number of nurses and support workers are anxious about the impact the changes in the immigration rules will have on them and their families. Some have reported that their employers are using the changes to intimidate them – and there is a real risk of staff being exploited as a result. This is happening in health care as well as for those who are working within social care settings. | Vi agreed to bring this to the attention of the SCNAC with a view of alerting the members to this and is offering help and support needed to manage this. If you would like to get in touch with Vi to discuss this further, please contact Sonia and she will put you in touch. | Vi Thomas | As necessary and convenient
2025-07-15 | Skills for Care Preceptorship Webinars | Skills for Care are scoping out the current landscape around preceptorship and will be running 2 webinars from September onwards. Each webinar will be run 3 times. All about promoting the development and implementation of preceptorship programmes generally | For more information, contact Lucy Gillespie on lucy.gillespie@skillsforcare.org.uk | Skills for Care | TBC
2025-07-15 | Nightingale Hammerson - Care Home Research Forum Thursday, 6th November 2025, 9:00AM to 4:00PM | Join Nightingale Hammerson, leading experts in residential, nursing, dementia and palliative care, as we explore the future of care and the importance of research in care homes. | https://nightingalehammerson.org/reach/research/chrf-2025/ | Nightingale Hammerson | 2025-11-06
2025-04-04 | Care Show London, London ExCel | Wednesday 30th April and Thursday 1st May 2025. Book your FREE ticket here: | https://care-show-london-2025.reg.buzz/scnac | SCNACs/ The OS | 30-Apr-25
2025-04-04 | LCAS at the Care Show | If you are attending the Care Show on 01May25 please join the LCAS RM Care Leaders & Registered Managers’ Live Show: | How to Lead with Confidence whilst Navigating Challenges - 13:30-14:00 in the Keynote Theatre | Peter Webb | 01-May-25
2025-04-04 | Pride Manchester | The Out Standing Diversity Forum, a division of the Outstanding Society, are excited to have been given 150 places to march at Manchester Pride this year. The requests to march with us for Adult Social Care / ballot for tickets will be opened at Care Show London on 30th April 2025/1st May 2025. You can book your FREE ticket here: | https://care-show-london-2025.reg.buzz/scnac | Out Standing Diversity Forum / The OS | 2025-04-30
2025-04-04 | Skills for Care - Student Nurse Placement | Alison Porteous has requested an update from Skills for Care on developing a strategy for having student nurse placements in Adult Social Care (see link aside) | https://www.skillsforcare.org.uk/search.aspx?q=nurse%20placements | Alison Porteous | Apr-25 |  | 2025-04-04
2025-01-17 | SCNAC Progress and Impact 6 months on | If you were not able to make our virtual progress meeting in January, you can listen again here: | https://www.youtube.com/watch?v=7qa5APv9BIw&t=3s | SCNACs | For Reference
2025-01-07 | Skills for Care - developing nursing placement guidance in Adult Social Care | Shared in chat: This may be helpful to share with nursing homes: | https://www.skillsforcare.org.uk/resources/documents/Regulated-professions/Nursing/Student-nurse-placements/Developing-nursing-placement-opportunities-in-social-care-v3-Final-180124.pdf |  | For Reference
2025-01-07 | RCN Guide around placements | Shared in chat: Guide is from 2006 but does have placement provider responsibilities | https://www.google.com/url?sa=t&source=web&rct=j&opi=89978449&url=https://www.rcn.org.uk/-/media/royal-college-of-nursing/documents/publications/2010/july/pub-001815.pdf&ved=2ahUKEwjdiNGz5-aKAxXtXEEAHSjXMMEQFnoECB0QAQ&usg=AOvVaw3uSA_RN_-RsnNYtv7NPtj3 |  | For Reference
2025-01-07 | NMC Preceptorship | For reference from chat | https://www.rcn.org.uk/Get-Help/RCN-advice/nmc-preceptorship | Millie Simms | For Reference
2024-06-25 | London Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/scnac-london-region/ | London SCNAC | Ongoing
2024-06-25 | RCN | For reference from chat: Dr Claire Pryor has been appointed as the RCN Foundation Chair in Adult Social Care Nursing and will be based at the University of Salford but will work across the four countries in the UK. | https://rcnfoundation.rcn.org.uk/Grants-and-funding/Chair-in-Adult-Social-Care-Nursing | RCN | For Reference
2024-06-25 | International Nursing from RCN | For reference from chat | https://www.rcn.org.uk/membership/Existing-members/International-nursing-members/Coming-to-the-UK | Millie Simms | For Reference
2024-06-25 | Skills for Care - Raising awareness of the role 'We Are Social Care Nursing | For reference from chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/We-Are-Social-Care-Nursing.aspx | Laura Anthony | For Reference
2024-06-25 | Contract checklist: 10 things to check before you sign | For reference from chat | https://www.rcn.org.uk/Get-Help/RCN-advice/contract-checklist | Millie Simms | For Reference
2024-06-25 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment |  | All | For Reference
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy | SCNACs | For Reference |  | 2024-06-19