## OPEN
NAME OF GROUP: EAST OF ENGLAND Region SCNAC (Social Care Nursing Advisory Council) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
27/09/2024 Pinned | Bios and Photos | Council members to please send high resolution photo and short bio (approx. 100 words) to be added to the East of England SCNAC web page | Send to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk). Go to the SCNACs webpages for examples | All | ASAP | https://theoutstandingsociety.co.uk/scnac/ https://theoutstandingsociety.co.uk/scnac-east-of-england-region/ 17Jul25 Council members reminded to send their bios and photos We would LOVE to be the first region to have ALL council members bios and photos on their webpage :) Raised at Apr-25 meeting.
2025-07-17 | Case Studies, Good News Stories and Upcoming Events | Forward case studies of people who choose to work in social care as their first employment to be added to the newsletter and webpage. Also looking for lovely outcome stories to share and information on forthcoming events. | Caron: caron.east@scnac.co.uk Victoria: victoria.east@scnac.co.uk Sonia: Admin.SCNAC@theoutstandingsociety.co.uk | All | As Available | Requested at meeting on the 17th July
2025-07-17 | Membership Gaps | Send contact details of potential new members to Caron, Victoria and Sonia | Caron: caron.east@scnac.co.uk Victoria: victoria.east@scnac.co.uk Sonia: Admin.SCNAC@theoutstandingsociety.co.uk | All | Ongoing | Care show contacts to be invited to the October meeting
2025-07-17 | Preceptorship Feedback | Provide feedback on the preceptorship programme to Sharon and Louise | If you need Sharon and Louises email address please contact Sonia | All | ASAP | Feedback given at meeting on 17th July- pilot nearly completed further update to come - next meeting
2025-07-17 | Preceptorship Evaluation | Identify a person in each home to support the evaluation of the preceptorship programme | in anticipation of national roll out after pilot completion | Participating Homes
2025-07-17 | Nursing Placements Update | Provide updates on the success of new adult social care nursing placements | student nurse placment strategy launch July - to be followd up at next meeting or/and in newsletter | Co-Chairs | At the Next Meeting | Co-Chairs will contact placment officers at all universities to provide a respurce for E of E services to arrange placements
2025-07-17 | Chief Nurse Awards | Encourage team members to submit nominations for the Chief Nurse Awards | https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms | All | ASAP | At meeting of 17 July and ongoing
2025-04-07 | Social Care Information on Learner's Healthcare App | Work with Davinia to replicate the Social Care information available for Norfolk on the Learner's Healthcare App for other areas. |  | Sara |  | Co-Chairs to revisit and meet with Sara
2025-04-07 | Social Care Promotion | Coordinate with Mary Edmonds to arrange a session at ARU to discuss the SCNACs and promote Adult Social Care to students |  | Caron / Victoria | When Convenient | Awaiting dates from Mary
27-Sep-24 & 12-Jul-24 | Medication Sustainability | How social care can put itself at forefront and create awareness around example. Draft work strands that people can add comments to | I.e Carbon footprint around inhalers vs. other means of managing asthma. Medication optimising route - money and planet saving. | Mike/ Helen | 2025-03-31 | See above actions where it states on target
2024-07-12 | Gaps in Membership | Quite Norfolk & Suffolk heavy on representation and need to include the whole of the East of England - so if anyone has good links with people across the region, please make introductions. |  | All | ASAP | See above- this is being followed up by Co-Chairs
2024-07-12 | Gaps in Membership | We are looking for an internationally educated nurse, another student nurse, early careers nurses, nurse associates, supported living. |  |  |  | Still working on this- will also be entered to newsletter. Has been raised with university contacts
2024-07-12 | Gaps in Membership | Charleen will introduce some nurse associates. |  | Charleen | ASAP | Has been contacted but no reply- will raise again at council meeting
2024-07-12 | Gaps in Membership | If anyone knows a healthcare worker or support worker who would be keen to join the council, please let us know. |  | All | ASAP | Raised at last council meeting- continue to work on this and invite
2024-07-12 | Gaps in Membership | Registered Care Managers, that are nurses | From a recent local nursing survey, Louise has a handful of names of people who are nurses but also registered care manager. Will contact them to make them aware of the council, invite them along and gather their views on priorities | Louise | Before next meeting | Continues to be communicated via managers forums. Chairs write to BWIC and invited colleagues to join and attend the council- no response received
2024-07-12 | Gaps in Membership | University Representation | UAE have been approached, but need to engage with others. If anyone has any contacts, please make introductions to chairs. | All | ASAP | Co-Chairs have emailed networks and may have a contact. January- this is being followed up.
2024-07-12 | Gaps in Membership | Access to data about who we are respresenting - how many LD nurses are there, how many nurses in nursing homes, how many individuals working out in supported living, domicilliary care and LD? Also overall workforce data set and different providers across the region, etc. | Fran to do some digging but there is an issue where by nurses often have dual roles - but will get an update, forward out any relevant reports and report back. | Fran | For the next meeting | Mar 2025 - Kate Letting unable to provide. CSC has emailed ARU contacts. Meeting on 24/03/2025 should be fruitful. Jun-25 - this is providing difficult to source from NMC/SfC due to the way the data is stored or the way it can be filtered. We will continue to explore ways to achieve this information
2024-07-12 | Education Pathways | Take any and every opportunity to get the word out about East of England SCNAC. Share the East of England page (see the updates and information page for the link) |  |  | Ongoing
2024-07-12 | Skills for Care | Please share information to be added in to our East of England website page. | Inspirational stories, useful links and information, etc. | All | Ongoing
2024-07-12 | Website Content

## Complete
NAME OF GROUP: EAST OF ENGLAND Region SCNAC (Social Care Nursing Advisory Council) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-04-07 | Resilience-Based Clinical Supervision (RBCS) | Direct any interested nurses in Adult Social Care to the FoNS website for nominations for the next cohort of RBCS | https://www.fons.org/programmes-development-opportunities/clinical-supervision/rbcs-programmes/ | All | ASAP | at last meeting of 17th July and in E of E newletter | 2025-07-28
2025-04-07 | Preceptorship Pilot Sites | Identify and select pilot sites for the preceptorship program in Adult Social Care |  | Sharon |  | pilot is underway and due to cmplete end of July | 2025-07-28
2025-01-15 | Medication Sustainability Feedback | Send out communications to care homes asking for feedback on current practices related to blister packs and other medication sustainability efforts. |  | Helen Hill | TBC | Poster completed awaiting introduction narrative. Follow up email sent | 2025-07-17
2025-01-15 | Medication Sustainability Resources | Share details of the glove reduction program in Norfolk and Waveney for inclusion in sustainability efforts. |  | Lisa Reid | TBC | Poster completed awaiting introduction narrative. Follow up email sent | 2025-07-17
2024-09-27 | Case Studies | Some short snappy case studies to use in social media | Highlighting different roles in social care and people who make this first choice after education. Preceptorship to build on. Local campaign to use nationally. Deborah Chapman has a colleague who may be able to help. | Chairs/Louise/ Sara | proposed date 21/02/2025 | Discussed at April meeting and will be discussed again at forthcoming meeting Replaced with new action from 17-Jul-25 meeting | ongoing
2025-04-07 | Action Point Log | This is the correct action point log for the East of England SCNAC - please delete previous copy sent with last agenda |  | All | ASAP | communicated to council members | 2025-05-28
2025-01-15 | Preceptorship Communication | Use existing communication methods that have been successful for teaching sessions to promote preceptorship initiatives. |  | Sharon Crowle | tbc | Meeting held and update given re new pilot. To be shared at council meeting | 2025-05-28
2024-07-12 | gaps in membership | Fran agreed to take away an action to talk to her colleagues and put the word out through registered manager networks, etc. |  | Fran | ASAP | Raised at managers forums wirth SfC | 2025-05-28
2025-01-15 | Preceptorship Policy | Coordinate with Sharon Crowell to ensure alignment of preceptorship policy with national guidance and local needs |  | co-chairs | tbc | follow up meeting held- see above | 2025-05-28
2024-09-27 | Headline priority: Attract and retain - Recruitment and Retention of nurses in social care. | First workstream to be Social care Preceptorship. This workstream will understand the environment for attracting and retaining nurses in social care. | This work will specifically focus on the role of preceptorship in supporting nurses new to social care, as a means of giving them fulfilling careers that help social care nursing retention. | Update Dec 2024 - - Fran moved to another assignment so Sara Harris has taken over | 2025-03-31 | Follow up meeting held- see above | 2025-05-28
2025-04-07 | RCN Foundation Grant | Circulate information from Claire Pryor about the RCN Foundation grants for quality improvement projects across networks | https://rcnfoundation.rcn.org.uk/Grants-and-funding/Research-and-practice-grants/RCN-Foundation-LV-Quality-Improvement-Project | All | ASAP | 02/05/2025 - shared at meeting in april and at care show | 2025-05-02
https://rcnfoundation.rcn.org.uk/Grants-and-funding/Educational-grants
2025-04-07 | Resilience-Based Clinical Supervision (RBCS) | Direct any interested nurses in Adult Social Care to the FoNS website for nominations for the next cohort of RBCS | https://www.fons.org/programmes-development-opportunities/clinical-supervision/rbcs-programmes/ | All | ASAP | 02/05/2025 - shared at meeting in april and at care show | 2025-05-02
2025-04-07 | Student Nurse Webinar | Share the link for the RCN webinar on interviewing techniques for student nurses taking place on 28th April | https://www.rcn.org.uk/news-and-events/events/stand-out-and-get-shortlisted-for-your-dream-job | Mary | ASAP | 02/05/2025 - CSC presented at this | 2025-05-02
2025-04-07 | Social Care Promotion | Coordinate with Mary Edmonds to arrange a session at ARU to discuss the SCNACs and promote Adult Social Care to students |  | Caron / Victoria | When Convenient | continues and both at care show | 2025-05-02
2024-07-12 | Gaps in Membership | Hertfordshire Care Providers Association | Umbrella organisation that all of the Hertfordshire Care Providers HAVE to register with. Might be a good connection. | Co-Chairs | ASAP | 10/02/2025 - VH will reach out but feels they may not have nurses 4/6/25 - VH met with them at the London Care show and eager to send a representative to the EoE Council, contact details scanned on the day | 2025-05-01
2025-04-07 | Student Nurse Webinar | Share the link for the RCN webinar on interviewing techniques for student nurses taking place on 28th April | https://www.rcn.org.uk/news-and-events/events/stand-out-and-get-shortlisted-for-your-dream-job | Mary | ASAP |  | 2025-04-28
2025-01-15 | Medication Sustainability | Produce a draft one-page leaflet (A1 attactive and inspiring flyer) on medication sustainability and simple, straightforward things that peopel can do to look at reducing their carbon footprint, including insulin pen recycling, salbutamol switching, and oral nutritional supplements | Resources are quite tight but Helen thinks that Stow Healthcare would be able support which is very much appreciated. Signpost to website (QR code) with additional information there. | Helen Hill / Mike Slator | 2025-03-31 | CSC met with project team on 4th Feb 2025- project feels on track for target date | emailed on 21/03/2025 for follow up meeting on final version
2025-01-15 | Preceptorship Policy | Coordinate with Sharon Crowle to ensure alignment of preceptorship policy with national guidance and local needs |  | Co-chairs | tbc | Chairs to arrange follow up meetings with priority lead. Follow up email sent after the Jan. meeting | follow up meeting on 24/03/2025
2025-01-15 | Membership Gaps | Consider hospice representation, dom care and NHSE East of England New Regional Chief Nurse to connect with Zena Aldridge to introduce the SCNAC Co-Chairs to Debbie Whittaker. | New email addressed for SCNAC Co-Chairs: Caron - caron.east@scnac.co.uk Victoria - victoria.east@scnac.co.uk | Caron Sanders-Crook / Victoria Hulstrom | April meeting | 10/02/2025 - CSC will follow up with Hospice contacts and VH will follow up with dom care contacts | 11/03/2025 and ongoing
2025-01-15 | Next Quarterly Meeting | Please note that the meeting original planned for 26Mar25 has been postponed, new date will be in April 2025 and will follow shortly. | If there are any events planned in April that would reduce attendance, please do let Sonia know (Admin.SCNAC@theoutstandingsociety.co.uk) and we will try and work around | All / Sonia | ASAP | Meeting arranged for 7th April 2025 | 2025-02-10
2025-01-15 | Preceptorship National Contact | Share contact details of Rachel Kumar, NHS nursing workforce programme manager, with Sharon Crowle for potential collaboration | From previous action point, Rachel Kumar's details for passing on are: Rachel Kumar, Nursing Workforce Programme Manager, Nursing Workforce and Implementation, Nursing Directorate, NHS England, E: Rachel.Kumar3@nhs.net | Caron Sanders-Crook | asap | Caron sanders-Crook sent details. | 2025-01-27
2024-09-27 | Second Regional Priority: Medication Sustainability | This workstream will understand how we can support integrated work between the NHS and social care to improve the sustainability of medication, by optimising its prescription and administration and reducing its carbon footprint. | This work will be led by Helen Hill, Stow Healthcare, and will be supported by Mike Slator (pharmacist), who will join the Council to support this project. This workstream is likely to look at current best practice in medication sustainability across NHS/social care and the potential to create an easy to use resource or guidance for use by social care and ICBs to promote ways in which those providing care can meet ESG goals, whilst providing choice and understanding of the carbon footprint of medication. | Helen Hill / Mike Slator | For next meeting - Jan 2025 | For January meeting, short proposal to be drafted to share with Council setting out existing best practice ideas and proposal for where the Council can add value | 2025-01-15
2025-01-15 | Preceptorship Engagement | Link up with locality managers for Registered Manager meetings to start conversations about preceptorship needs and support |  | Sara Harris | tbc | 21/03/2025 Sara Harris has declined any further input. Sara harris sent email with meeting dates for some meetings Chairs to arrange follow up meetings with priority lead. Follow up email sent after the Jan. meeting | closed
2024-07-12 | Gaps in Membership | Eastern Region Care Providers Alliance | Just created - linking all care associations in the region. Fran to source contacts and introdue to Chair/Co-Chair | New chair | ASAP | Jan 2025 emailed by Caron Sanders-Crook. Sandie Oxborrow (sandie@scaservices.org.uk) to be contacted by new chair | 2025-01-10
2024-07-12 | NHS East of England Workforce Transformation (used to be HEE - Heatlh Education England) and other established groups | Helen Wright asked in the chat if Sharon Crowle has been invited to the SCNAC from Norfolk ICB | We have contacts with now. Regional CNO participation would be good. | New chair | ASAP | Jan 2025 - Victoria, Caron and Sara have met Sharon and established a connection and actions going forward. Sharon Crowle was contacted and contact details with Sonia Pritchard to pass to new chair and co-chair | 2025-01-08
2024-09-27 | East of England Chair and Co-Chair Roles | Helen and Louise have stepped down from their roles - moving forwards and looking for expressions of interest | Expressions of interest to Sonia Pritchard (Admin.SCNAC@theoutstandingsociety.co.uk) | All | ASAP | Victoria Hulstrom and Caron Sanders-Crook appointed as Co-Chairs | 2024-12-01
2024-07-12 | Spreading the word about SCNACs and Social Care | Liaise with other established groups when we cross paths to establish links and share information. | Send any useful links / information to Helen/Louise/Sonia to be shared with the SCNAC as appropriate. Fran to make introductions to Debbie Cubbitt from NHSE to look at how we can link with their regional structure and groups. | New chair | Ongoing | Jan 2025 - Debbie Cubitt was contacted by Caron Sanders-Crook and Victoria and Caron have met with many colleagues from NHSE and started connecting them togeher across the region and country. Plan to Invite Rachel Kumar , Nursing Workforce Programme Manager, Nursing Workforce and Implementation, Nursing Directorate, NHS England, E: Rachel.Kumar3@nhs.net M: 07872815795 to next meeting to connect across Debbie Cubbitt was contacted and contact details with Sonia Pritchard to pass to new chair and co-chair | Completed and Ongoing
2024-07-12 | Fly on the Wall Coverage | If anyone knows any producers that might like to do a fly on the wall series about Adult Social Care - please do make the suggestion!! |  | Helen Wright |  | Ruth feels better to drop this to promote different case studies. Helen Wright has contacted a team re. this but no response. If they respond, will bring it back to the table. | Parked for now 27-Sep-24
2024-07-12 | Terms of Reference (ToR) | If no amendments are requested, draft ToR will be adopted and uploaded to our webpage |  | All | 2024-08-23 | No issues raised after July meeting. To be uploaded. | 2024-09-27
2024-07-12 | Next Meeting | Please note the change of date for the next meeting - the invitaion has been amended, but please make sure your electronic diaries have been updated! | Friday 27th September 2024 from 1.00-2.30pm | All | 2024-09-27 |  | 2024-09-27

## Updates and Information
NAME OF GROUP: EAST OF ENGLAND Region SCNAC (Social Care Nursing Advisory Council) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-07-30 | Skills for Care Preceptorship Programme | Preceptorship programmes are a vital part of the support required to recruit and retain registered nurses and nursing associates who are new to the NMC register. Join the webinar on September 3 which will introduce you to the principles of preceptorship. You’ll hear from Wendy Fowler, Nursing Education Advisor at the Nursing and Midwifery Council (NMC) as she offers guidance and practical tools and tips for your organisation. There are also two separate sessions, running through September, October and November, for those people in your nursing team who could carry out the following roles - one would be a preceptorship lead, who would lead on this for the organisation, and then other nursing staff who could act as preceptors. | What your organisation needs to know to be preceptorship ready: https://www.skillsforcare.org.uk/news-and-events/Events/September/Preceptorship-programme-what-your-organisation-needs-to-know-to-be-preceptorship-ready.aspx | Skills for Care | 2025-09-03
|  |  | Preceptorship lead workshop - embedding and chapioning preceptorship: https://www.skillsforcare.org.uk/news-and-events/Events/September/Preceptorship-lead-workshop-Embedding-and-championing-preceptorship-September.aspx | Skills for Care | 29-Sep-25 21-Oct-25 26-Nov-25
|  |  | New to Role preceptor workshop. The preceptor role in practice: https://www.skillsforcare.org.uk/news-and-events/Events/September/New-to-role-preceptors-workshop-preceptor-role-in-practice.aspx | Skills for Care | 30-Sep-25 22-Oct-25 27-Nov-25
2025-07-29 | RCN Key Changes to Immigration Policy Webinar | The webinar will give attendees a better understanding of the changes to the UK’s immigration rules and assist with questions on: - Increases to the immigration salary threshold, and the impact on those in NHS Band 3 roles and in the care sector. - Changes to rules around family dependents for roles which are RQF levels 3-5. - Changes to rules for sponsoring care workers. - Government proposals on indefinite leave to remain. | The booking link is: https://www.rcn.org.uk/news-and-events/events/immigration-update | RCN | 2025-08-19
2025-07-17 | NIHR Researcher Development Programme for Social Care Nurses | Shared in the chat by Victoria Hulstrom | https://www.nihr.ac.uk/researcher-development-programme-social-care-nurses | NIHR | for Reference | PLEASE NOTE: Applications are now closed and the successful applicants will be announced by late-August 2025
2025-04-07 | RCN - Exploring Careers Within Social Care: Complex Domiciliary Care | Shared in the chat by Sarah Seeley | https://www.rcn.org.uk/news-and-events/events/exploring-careers-within-social-care-complex-domiciliary-care | Sarah Seeley | For Reference
2025-04-07 | RCN - Stand Out and Get Short-Listed for your Dream Job | Shared in the chat by Sarah Seeley | https://www.rcn.org.uk/news-and-events/events/stand-out-and-get-shortlisted-for-your-dream-job | Sarah Seeley | For Reference
2025-01-15 | Antipsychotic Posters | Shared by Zena Aldridges | Sent as separate attachment with email |  | For Reference |  | 2025-01-27
2025-01-15 | STOMP - Stop Over Medication of People | Louise signposted people to this programme during the meeting - particularly for people with a learning disability and autisic people. More information here: | https://www.england.nhs.uk/learning-disabilities/improving-health/stomp-stamp/ |  | For Reference
2025-01-15 | NIHR Social Care Leadership Awards | Zena shared details and signposted to the Research category | https://www.socialcaretop30.co.uk/scl/categories/ |  | For Reference
2025-01-15 | Employer Link Service Adviser | Kate Lettin shared in the chat that the NMC are recruiting for a new role in her team. Employer Link Service Adviser, working across the East of England with a specific focus on social care. (NMC are recruiting 7 new advisers in total across UK) It may be of interest to people in our networks and closes on 19th Jan. | https://nmc.pinpointhq.com/#js-careers-jobs-block | Kate Lettin | 2025-01-19 | no longer active | 2025-01-27
2025-01-15 | Sustainability and Incontinence Products | Shared in the chat by Zena Aldridge | https://www.bbuk.org.uk/sustainability-and-incontinence-products/ |  | For Reference
2025-01-15 | Norfolk Care Careers - Traineed Nurse Associates | Shared in the chat by Helen Hill | https://www.youtube.com/watch?v=61MrmUbLS-w |  | For Reference
2025-01-15 | Norfolk Care Careers - Clinical Lead | Shared in the chat by Helen Hill | https://www.youtube.com/watch?v=ARgKaYKjr2k&t=2s |  | For Reference
2024-09-27 | Social Care Nurses 'Critical' - NT Article | For Reference | https://www.nursingtimes.net/news/social-care/social-care-nurses-critical-to-incoming-healthcare-overhaul-12-09-2024/ | All | For Reference
2024-09-27 | SCNACS Celebration Event - 12th September 2024 | For Reference | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ | All | For Reference
2024-09-27 | Skills for Care Event: The adult social care sector and workforce in Central and Eastern England 2024 Tuesday 12th November 2024 from 10.00am-11.45am on Zoom | Each year, we produce important insights about the adult social care workforce on a national, regional and local level. These insights are used to inform planning, funding and decision making across the sector. In October we will be launching our latest State of the adult social care sector and workforce in England report along with new regional data. At this event you will hear the headline findings from your regional data and what they mean for you - including the size and structure of the workforce, recruitment and retention trends, local workforce demographics, pay and training. You will also hear how the data is used to inform workforce planning and how you can access and use our data throughout the year. This event will be looking specifically at the data from the: • West Midlands • East Midlands • Eastern region During the session delegates will be invited to join breakout rooms to hear further information about the data relevant to the area that they are located in. | Shared by Fran Simons from Skills for Care (Fran.Simons@skillsforcare.org.uk) https://events.skillsforcare.org.uk/skillsforcare/frontend/reg/thome.csp?pageID=644428&eventID=2003&traceRedir=2 | All | 2024-11-12 | no longer active | 2025-01-27
2024-09-27 | Digital Care Hub | Core goal free support and guidance to providers. Free support with digital and cyber | Digital records to all CQC providers in England. Programme for data security and protection toolkit. Working with Oxford University on responsible use of AI in social care. | Katie Thorn
|  | Where can we add value in digital space. More support in the sector to prepare more for cyber security. Minimum data specifications report. | Digital care hub - Ran by social care providers. katie@digitalcarehub.co.uk Norfolk and Waveney are already running NEWS2 digital system and can share work done - Deborah Chapman | Katie Thorn/ Ruth
2024-09-27 | ICB | Working collectively on out of hospital model - Testbed for NHS. Presentation here in the future. | Listening to homes on what they are doing well. Facilitating meetings for care homes with other care homes. Looking at homes that are going into crisis. Work with admissions avoidance. Working on champions networks. | Ruth/ Carol / Mary
2024-09-27 | From the chat: | UEA contact seeking to challenge perceptions of nursing via local marketing campaign | Simon.Rose@uea.ac.uk
2024-09-27 |  | Preceptorship | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Preceptorship.aspx
|  | Dee and Helen to catch up regarding virtual ward work Links that can be made within Norfolk between teams to promote each other. Deborah to link with Fran. Fran.simons@skillsforcare.org.uk | https://www.skillsforcare.org.uk/Workforce-Strategy/Home.aspx
|  | Tech and digital skills | https://www.ipsos.com/sites/default/files/ct/publication/documents/2021-12/NHSX_Technology_and_Digital_Skills_Review_Main_Report_November_2021.pdf
https://beta.digitisingsocialcare.co.uk/minimum-operational-data-standard-mods
https://beta.digitisingsocialcare.co.uk/reporting-minimum-data-specification-rmds
|  | Different Nursing Careers in Social Care | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Nursing-careers-in-social-care/Nursing-careers-in-social-care.aspx
2024-07-12 | East of England Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/scnac-east-of-england-region/ |  | For Reference
2024-07-12 | Main SCNAC Page | Resources available - there are a number of podcasts, and a number of different ways of understanding a bit more about what the Social Care Nursing Advisory Council objectives are about. | https://theoutstandingsociety.co.uk/scnac/ |  | For Reference
2024-07-12 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference
2024-07-12 | ASC Workforce Strategy | Shared in the chat: Is being streamed live and you can book to watch live: | https://events.skillsforcare.org.uk/skillsforcare/frontend/reg/thome.csp?pageID=617548&eventID=1924&traceRedir=2 | All | For Reference
2024-07-12 | NMC Resources | In January 2024 NMC announced that they would be commissioning research into nursing and midwifery students’ practice learning requirements. To sign up for updates: | https://r1.dotdigital-pages.com/p/129A-1B4W/practicelearning |  | For Reference
2024-07-12 | Skills for Care Resources | Skills for Care have updated their nursing web pages recently and have some new nursing career stories looking at different careers in nursing in social care | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Nursing.aspx |  | For Reference
2024-07-12 | NMC Newsletter | The NMC publishes a range of newsletters and we're currently speaking to Zoe Watson about interviewing a student nurse in social care placement for a future feature: You can sign up using the following link: | https://www.nmc.org.uk/news/email-newsletters/ |  | For Reference
2024-07-12 | UEA - University of East Anglia | Shared in the chat: The UEA are trying to shift the narrative from NHS being the only career pathway. Social Care was supposed to be a part of this and I am furthering a conversation on it. It would be great to have something built that all education providers could use.. | https://www.uea.ac.uk/this-nurse-can?utm_source=google&utm_medium=performancemax&utm_campaign=ug2025_nursing&gad_source=1&gclid=EAIaIQobChMIs_ntzJahhwMVSphQBh3CBAyyEAMYASAAEgL8h_D_BwE
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy |  | For Reference