## OPEN
NAME OF GROUP: MIDLANDS Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
02-07-24 Pinned | Council Members Bios and Photos | Please submit your high resolution photos and short bios (approx. 100 words) to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to be included on the website | Would be grateful if you could put 'Midlands' in the subject line | All | ASAP | 20 Aug 24 Minutes and action points to be circulated to all members. 29-Oct-24 Bios received from several council members but not yet added to Regional SCNAC page by OS. 14Jan25 - Reminder to all council members to submit their photos and bios if they have not done so already. 22Jul25 - would love to be the first region to have a full house of photos and bios on the web page!
2025-07-22 | BSol Development programme | Louise Luckman to share with SCNAC for comments. Katie Welbourn to work with Louise. Jacqueline Barnes to corodinate work | Meeting outside of SCNACs to develop resource | Louise luckman/Katie Welbourn/Jacqueline Barnes | Update at next meeting
2025-07-22 | Chief Nurse Awards | Encourage team members to submit nominations for the Chief Nurse Awards | https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms | All | ASAP
2025-07-22 | Professional Care Workers Week | Submit nomiations for individuals or teams to be recognised during Professional Care Works Week in September |  | All | When Convenient
2025-07-22 | CNO Strategy Review | To share the updated CNO strategy once it is reviewed and refreshed by the end of September |  | Jacqueline Barnes | End-Sept
2025-07-22 | 10-Year Plan Infographics | Share the infographics relating to the 10-year plan and the Dash Review to the group | Send to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to disseminate to the group | Jaqueline Barnes | ASAP
2025-07-22 | Student Nurse Vacancies | Consider any roles that could be open for newly qualified nurses and share them on the regional platform |  | All | When available
2025-07-22 | Transition to Practice Workshop | Share the NMC position on newly qualified nurses accepting healthcare assistant roles with the group |  | Tony Newman | ASAP
2025-07-22 | Digitising Social Care Programme | To get involved contact Katie at Digital Care Hub and she will put you in touch with the team at DHSC. | Katie Thorn: katie@digitalcarehub.co.uk Katie also suggests emailing GetAdultSocialCareData.team@dhsc.co.uk to subscribe to their monthly update newsletter | Katie Thorn / DHSC | ASAP
2025-07-22 | Dysphagia | To share Clinical Learning Alert on Dysphagia with council members | Sent to Jo-Anne (jo-anne.midlands@scnac.co.uk) or Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to disseminate. | Louise Luckman | When Convenient
2025-07-22 | Updated Development Programme | Send to Sonia to disemminate to council members for feedback |  | Louise Luckman | ASAP
2025-05-07 | CQC Inspection Issues | Escalate the issue of delayed CQC inspections and its impact on social care providers to Deborah Sturdy for further action. |  | Anita Astle / Jo-Anne Wilson | ASAP | Jo-Anne has discussed with Johnathon Parry CQC Operations manager. There is to be a series of provider Engagement meetings in July to share up to date developments
2025-05-07 | Nottinghamshire's Dysphagia Training Pack | Contact Nottingham for their training pack on dysphagia and choking prevention. Share with the council |  | Anita Astle | When Convenient
2025-05-07 | South Warwickshire's SALT Training | Share link with council |  | Jo-Anne Wilson / Samantha Preston | ASAP | Training curently being updated but will share once new trianing available
2025-05-07 | Suggestion of agenda item for next meeting | Presentation of example of neighbourhood working | Jacqueline suggested that Katie aske the WT Team to see if they can bring their nursing staff and local social care nurses to present about how they work together in practice (72 hours support model and pathway work) | Katie Welborn / Jacqueline Barnes | July Meeting
2025-05-07 | Create a Repository |  | Jacqueline and Samantha offered to help with this to include brining members forward from the region who have solutions and best practice to share. | Anita Astle / All | Ongoing Update at July Meeting
2025-05-07 | Workstreams | Jacqueline Barnes would be keen to understand the workstreams to aligh with other Midlands work |  | Jacqueline Barnes / Vicky Sandy-Davies | As Convenient
2025-05-07 | AI and Social Care | Provide a guide on different AI tools that managers and deputies can use to reduce their workload |  | Katie Thorn | When Convenient
2025-05-07 | AI and Social Care | Connect with Jacqueline to discuss integrated neighborhood teams and AI opportunities |  | Katie Thorn / Jacqueline Barnes | When Convenient
2025-05-01 | Skills for Care Network Survey | Please can all council members complete this survey by Monday 12th May 2025 | https://online1.snapsurveys.com/Interview/967ca879-e7e8-46af-9b3d-8f579fb8df16 | All | 2025-05-12 | survey closed
2025-01-14 | Social Care Networks | Put out a call to all ICBs to gather information about different networks and opportunities for social care involvement. |  | Anita Astle / Jo-Anne Wilson | On hold | Due to changes within ICB's at present, this item is on hold until new ICB workign arrangements have been decided and implemented | On hold
2025-01-14 | Benchmarking Collaboration | Arrange a conversation with the VIVALDI project to explore collaboration on benchmarking information. |  | Anita Astle | Before next meeting
2025-01-14 | Benchmarking Priority | Circulate the minutes from the past two meetings on benchmarking and raising standards in social care. | Forward to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to be shared with the action points from todays meeting | Anita Astle | 2025-01-24
2025-01-14 | Regulation 9A Guidance | Discuss with Deborah Sturdy and Duncan Burton to create and publicise guidance on Regulation 9A for social care providers. |  | Anita Astle / Jo-Anne Wilson | At Earliest Convenience | O/S, Diane Mayhew and Jo-Anne to do a podcast highlighting reg 9A
2025-01-14 | Regulation 9A Awareness | Escalate the issue of inconsistent implementation of Regulation 9A to all CNOs and discuss with UKHSA |  | Lynne Bowers / All | ASAP
2025-01-14 | Regulation 9A Training | Check if Skills for Care has any guidance on Regulation 9A and share link with the group (via Admin.SCNAC@theoutstandingsociety.co.uk) |  | Shirley Way | ASAP
2025-01-14 | Community of Practise | Tony Newman to put the SCNAC in touch with Helen Bailey for Social Care to be involved in this project. Will introduce on Linked In | Meeting will be in March 2025 and Tony will | Tony Newman / Anita Astle / Jo-Anne Wilson
2025-01-14 | Showcasing Quality Improvement Workstreams | For nurses across the sector - NHS or Social Care. Showcase ideas and work from the Midlands | Black Country ICB and Northamptonshire keen to support Jo-Anne to contact Katie and Gabriella | Jo-Anne Wilson Katie Welbourn Gabriella Okeeffe | ASAP
2025-01-14 | Research Introductions | Lynne Bowers, ADASS to introduce Anita and Jo-Anne to Victoria Hall and Kelly Stoker from UKHSA | Victoria and Kelly have been working on two research projects (including VIVALDI) and are interested in infection prevention and control - Thy are wanting to improve data | Anita Astle / Jo-Anne Wilson / Lynne Bowers | ASAP
2024-07-02 | Council Members Bios and Photos | Please submit your high resolution photos and short bios (approx. 100 words) to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to be included on the website | Would be grateful if you could put 'Midlands' in the subject line | All | ASAP | 20 Aug 24 Minutes and action points to be circulated to all members. 29-Oct-24 Bios received from several council members but not yet added to Regional SCNAC page by OS. 14Jan25 - Reminder to all council members to submit their photos and bios if they have not done so already.
2024-10-01 | Workforce Strategy | Implementation stage - Presentations from working groups to get people thinking broadly | One pager to be sent out to Anita/Jo Anne by Shirley Way SfC. Turnover and vacancy rates high. Working with local care associations and universities - all to have placements. | Anita/ Lynne Bowers | Early Nov | 29-Oct-24 Anita Astle and Lynn Bowers are attending 4 Career Academy workshops arranged by Partners in Care and Health (PCH) and Local Government Association (LGA) to inform shaping a Social Care Academy. Awaiting information from Shirley Way who is on leave.
2024-10-01 | Regional Priorities | 1) The use of Digital Technology to benchmark care practices and to support quality improvement. 2) Forming a Social Care Academy that meets the needs of the Midlands Providers and workforce. | Form working groups for each One date for each 2 weeks apart. Aim to meet 3 times before our next regional meeting on 14th January 2025 | Digital: Anita Academy: Jo-Anne | 2025-07-01 | Digital Social Care meeting dates 8-Nov-24 and 13-Dec-24 Social Care Academy meeting date TBC
2024-10-01 | Social Care Academy | Look at existing academies - how to bring primary care closer to social care. Link with Katie - joining forces. | There is a national Social Care (or Career) Academies Community of Practice hosted by LGA Partners in Care & Health. There are 60 social care academies. People use multi funding schemes. Specific workshops. | Lynne/ Anita / Shirley/ Katie/ Jo-Anne/ Danielle | Early Nov | meeting planned for 6.12.24
2024-10-01 | Social Care Academy | Joining working party to look at what is possible around workforce and academies. | Volunteers: Shirley Way, Diane Mayhew, Jasmine Stanhope, Lynne Bowers, Andrea Westlake, Jayanthi Antony, Shanci Mathew, Vicky Sandy–Davis, Lynn Tolley will ensure someone represents SSOT system, Katie Welborn, Fran Otolo, Danielle Fullwood | Jo-Anne Wilson | Early Dec | Meeting to be arranged after pre-meeting with Lynne, Jo-Anne, Katie and Anita. Invitation out for 10th January 2025
2024-10-01 | Data Collection | Would data collection help and capture practices to improve. Work on this re. digital | Do we need more care homes who are experts in EOL care? How do we achieve. Population data means need to innovate. | Volunteers: Andrea, Diane, Katie T, Shanci, Shirley, Lynne with Claire Smout, Jayanthi | End Dec-24 | This will be explored within our Digital Social Care meetings planned for 8-Nov-24 and 13-Dec-24. |  | hay
2024-10-01 | Training and Research | Strategy should be developed in partnership with HSE to grow and develop workforce. Evaluation of priorities. Wanting Adult Social Care to be prioritised. | Supporting delegated healthcare tasks. Leadership programme. How do we ensure implemented - ADAS/Regional people board level. Identify gaps and working together to meet needs. Clinical skills training. | All | 2025-07-01 | This will form part of our Social Care Academy work.
2024-10-01 | Define Adult Social Care | Re educating people of importance | Get to people ahead of needing care, change mindset and culture of what we are trying to achieve. Workforce piece - bringing framework together. Strip back to fundamental nursing piece and career pathway (see update aside from Anita) | All | To be discussed in 3rd Quarterly Meeting | These are the definitions used by Zena Aldridge (NIHR): Definition: ‘Social care nurses are registered nurses who practice in environments outside of the NHS, more often for independent sector organisations. Whilst the majority work in residential care settings, others may practice within settings such as charitable organisations, local authorities, faith groups and education.’ Narrative: ‘Social care nursing focuses on providing care embedded in a biopsychosocial model which is relationship and/or person-centred care and which seeks to meet a person's health and social care needs in totality. Social care nurses usually refer to those in their care as ‘people’ or ‘residents’ (in residential care settings) not ‘patients’. This differs from many other areas of healthcare which are more readily sited within a biomedical model, where there is primary focus on addressing physical health needs, often in isolation within the context of a singular disease or problem.’
2024-10-01 | Defining Roles | Define the role of ASC Nurse | Would assist in raising profile and specialist skill set that is required. Make more insightful and attractive career option. Long term workforce benefits (see update aside from Anita)
2024-10-01 | Raising Standards | 1. Social care workforce and workforce community academy. Community of practice. 2. Digital care planning systems to benchmark care practices to support quality improvement. Capturing relevant data. Evidence based practices. | Up to date data needed on who is in care homes, what they need and what matters to them. A way to easily capture data easily on day to day basis. Work with digital care planning companies to create interoperable programme. | Digital: Anita Academy: Jo-Anne | 2025-07-01 | Digital Social Care meeting dates 8-Nov-24 and 13-Dec-24 Social Care Academy meeting date TBC
2024-10-01 | Recruitment and Retention | Monthly tracker - Around ICBS | Main reports are annual but these are monthly. Need more registered nurses and associates. Integrated teams, better development pathways, rewards and recognition needed. Joined up action on pay. Retaining more internationally educated nurses. | Digital: Anita Academy: Jo-Anne | 2025-07-01 | Capturing data is part of the work required for both of our regional priorities. We anticipate this data will be more meaningful as we gain wider engagement and clearer strategic approaches to both of our regional priorities.
2024-10-01 | Work with Climate Action Charities | Lynne/Jo Anne to lead. A golden thread through other priorities. EDI as a thread as well as an ethical thread too. | Several professional groups/organisations have Sustainability forums: National Care Forum, QNI, Centre for Sustainabile Healthcare. Jo-Anne has links into to these forums and attends meetings. Work with Lucy Brown to establish a Social Care Sustainability forum within Centre for Sustainable Healthcare Tom Rose - Ethical thread in sustainability as well. Carbon Footprints within companies - Any academic proof send to Katie Thorn | Lynne / Jo Anne/ Katie/Lucy | 2025-07-01 | Attendees agreed sustainability was important but a huge piece of work in itself. It was agreed that where we can weave this into each of our two priorities that we should. This focus may not be evident until we establish work towards each priority. Jo-Anne working as part of the development group for Greener Palliative Care Awards. Galanos House (RBL) one of 4 community Hubs participating in 'Reducing Medication Waste in Care Home' with Centre for Sustainable Healthcare supported by the Q Exchange
2024-07-02 | Additional Members | Review list of key, inspirational, motivated, dedicated infulential managers that want to be part of the group sent to Anita by Louise Luckman in May 2024 | Louise will resend email to Anita (chair.midlands@scnac.co.uk) is happy to make introductions | Louise / Anita | ASAP | 13 Aug 24 met with Karina Bennion (Stoke & Staff) Follow up Louise Luckman's recommendation 01Oct24 - CNO 2 reps now so all fine. CNOs meet weekly - ask for slot at their meetings. Lynne to approach regional chief nurse to ask re. slot. Date booked for 14-Nov-24
2024-07-02 | Gaps in Memberships | Aim to make sure that no ICB footprint is left untouched or unrepresented | 14.Birmingham & Solihull - Louise Luckman 15.Black Country & West Birmingham - Katie Wellborne 16.Coventry & Warwickshire - Ellie Monkhouse 17.Joined Up Derbyshire - Professor Dean Howells 18.Herefordshire & Worcestershire - Kathryn Cobain 19.Leicester, Leicestershire & Rutland - Kay Derby 20.Lincolnshire - Tony Vine 21.Northamptonshire - Gabriella Okeeffee 22.Nottingham & Nottinghamshire - Diane Kareen Charles 23.Shropshire, Telford & Wrekin - Vanessa Whatley 24.Staffordshire - Becky Scullion Represented at the meeting in black / Not represented at the meeting in red | Anita / Jo-Anne | Ongoing | 20 Aug 24 Awaiting appointment of CNOs or relevant contacts. 29-Oct-24 Jo-Anne and Anita are meeting all ICB CNOs on 14-Nov-24 and hope to have all CNOs engaged post this meeting *Ellie Monkhouse CNO NHS COVENTRY AND WARWICKSHIRE ICB ellie.monkhouse1@nhs.net *Professor Dean Howells CNO NHS DERBY AND DERBYSHIRE ICB dean.howells@nhs.net
|  | Need: Supported Living Organisation Domiciliary Care Representation Early Careers Nurse Residents | If anyone has suggestions of people to approach, please make the appropriate introductions to Anita (chair.midlands@scnac.co.uk) and Jo-Anne (co-chair.midlands@scnac.co.uk) | All | ASAP | 20 Aug 24 Early careers Nurse identified and agreed. 20 Aug 24 Domicillary Care representation identified and agreed. 29-Oct-24 Membership is continuing to grow. We still require a Supported Living Organisation and Residents.
2024-07-02 | Local Priorities | National priorities have been adopted (see updates and information), as a region we need to adopt one or two local priorities that sit comfortably across all of our ICBs | See some of the suggestions given in the Attendance Document Please submit your suggestions to us and we might send out a poll. |  |  | 02 Jul 24 Workforce Development & Raising Profile of Social Care 01 Oct 24 - Skills for Care hold lots of data. New data launched. Has operational workforce planning toolkit - link to this. 10th October. May be a few changes. 12th Nov regional launch. Shirley to send link out to book on. Link for workforce intelligent also. | 2024-10-01
2024-07-02 | Extending the Nursing Network | Shirley suggested looking at this with Louise and Lucy |  | Louise / Lucy / Shirley |  | 20 Aug 24 Exploring Midlands Social Care Nurse Facebook Group 22-Oct-24 Social Care Nurses met with Anita and Jo-Anne and felt a secure social media group for Midlands Nurses to connect with one another was a good idea. Survey to be completed to see whether SC Nurses want such a group.
2024-07-02 | Social Care Nursing Advisory Council (SCNAC) | Create more awareness about SCNAC among social care nurses. | This might help to attract more involvement. | Anita/Jo-Anne/Shirley/Vicky/ Samantha | Ongoing | 02 Jul 24 working with ICBs, SfC & RCN to promote Midlands SCNAC
2024-07-02 | Good News Stories | Rights for Residents are about to ask their appox. 8000 members to share their good news stories and Diane will share accordingly |  | Diane | When available
2024-07-02 | NMC - International Nurses - Welcome to the UK Workshop | Workshop has been developed by NMC over the last year. If you would like more details please let us know and we can put you in touch with Tony Newman | Designed and aimed directly at international nurses to talk to them about some of the ethical and cultural changes and differences they will experience practising in the UK. Been rolled out to ICB's and trusts, but equally it should be offered to the Social Care network as well. | All / Tony | As required | 20 Aug 24 Anita to contact Tony Newman NMC for more detail
2024-07-02 | Prescribing | Katie is exploring from a governance perspective in terms of prescribing, how they migrate or expand what we're already doing in primary care? | If we can do it in primary care, why can't we do it in the independent sector if we've got an overarching governance framework that is there to support the growth through the business Academy? Will bring back to the group her findings. | Katie | When complete | 20 Aug 24 Anita and Jo-Anne to catch up with Katie.
2024-07-02 | Website Content | Please share good news stories and examples of best practice and we will add these to our webpage (including care awards, winners, finalists from your areas) | Again please forward any stories to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) and put 'For Midlands Webpage' in the subject line | All | As available | 20 Aug 24 Request good news stories when circulating minutes. 01Oct24 - Nominate for CNO awards - link shared.
2024-07-02 | Communication | Everyone on the call was happy for the group to communicate through email. If any has any communication suggestions - either a Whats App group or a facebook page, please send across your suggestions to Anita and Jo-Anne. |  |  | Ongoing | 20 Aug 24 Galanos House gained GSF Platinium Accreditation for 6 time! Wren Hall gained Veteran Friendly Framework accreditation. 01-Oct-24 Requested good news stories.
|  | Suggestion to set up a Midlands Network for Nurses or possibly tap into/promote an existing group | Lucy McDonald at Skills for Care has recently set up a What's App group for Social Care Nurses. Could this be regional? Tom suggested it should NOT be on What's App There will also be a secure area on the website that is currently being developed. | Anita / Jo-Anne / Shirley (Skills) |  | 20 Aug 24 Exploring Midlands Social Care Nurse Facebook Group 22-Oct-24 Social Care Nurses met with Anita and Jo-Anne and felt a secure social media group for Midlands Nurses to connect with one another was a good idea. Survey to be completed to see whether SC Nurses want such a group.
|  | Please forward any suggested agenda items / items for discussion at the next meeting to Anita and Jo-Anne | Anita - chair.midlands@scnac.co.uk Jo-Anne - co-chair.midlands@scnac.co.uk | All | Before next meeting | 20 Aug 24 Request agenda items when circulating minutes.
2024-07-02 | Registered Managers vacant posts | Provide Skills for Care figures on this to the group |  | Shirley | As available | 01-Oct-24 No update.

## Complete
NAME OF GROUP: MIDLANDS Region Social Care Nursing Advisory Councils (SCNACs) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-05-07 | AI and Social Care | Share the upcoming guidance on AI use in care homes once it is signed off by the DHSC comms team |  | Katie Thorn | When Available | update shared at July meeting | 2025-07-22
2024-10-01 | Chief Nurse Adult Social Care Awards | Deborah Sturdy emphasised the need to nominate your excellent team members at all levels. Doesn't have to be nurses - All applications considered. | Criteria: https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms/chief-nurse-adult-social-care-awards-nomination-criteria Nomination Form: https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms | All | Ongoing and ASAP | At each meeting we ask attendees to make nominations for Chief Nurse Awards. Deborah presented Wren Hall Nursing Team with a Chief Nurse Team Award. JW has nominated several times but not heard anything back yet. 14-Jan-25 All members were reminded to submit Chief Nurse Award Nominations Superceded with new action point from Jul25 meeting | 2025-07-22
2025-05-07 | AI and Social Care | Share the slides from presentation |  | Katie Thorn / Sonia Pritchard | With meeting follow up | Shared with meeting follow up | 2025-05-23
2025-05-07 | VIVALDI Social Care Research Project Care Home Visit | If anyone is interested in attending, please do let Sonia know - Admin.SCNAC@theoutstandingsociety.co.uk. Ruth Endacott will be in attendance and it would be a great opportunity for anyone local to find out more about the VIVALDI project. | Cavendish Park Offenham Road, Evesham WR11 3DX Below is the schedule for the afternoon: 2:00 – 2:30 ¦ Arrival & Welcome Drinks 2:30 – 3:00 ¦ VIVALDI Social Care Presentation 3:00 – 3:30 ¦ Tour of the Home – Meet Residents and Staff 4:00 ¦ Departure | VIVALDI Team | 2025-05-16 | visit completed | 2025-05-16
2025-05-07 | Choking Incidents | Share the lessons learned from the coroner's report on choking incidents with Sonia for wider dissemination. |  | Jo-Anne Wilson / Sonia Pritchard | With meeting follow up | Completed | Completed
2025-05-07 | Meeting Scheduling | Schedule the next three meetings and inform all members of the dates. |  | Jo-Anne Wilson / Anita Astle / Sonia Pritchard | 2025-05-23 | scheduled and invitations out to council members | Completed
2025-01-14 | FoNS RBCS - Resilience Based Clinical Supervision | Deborah Sturdy encouraged everyone to grasp this opportunity with both hands as it's free! | https://www.fons.org/programmes-development-opportunities/clinical-supervision/rbcs-for-social-care/ | All |  | Shared at May meeting | 2025-05-07
2025-01-17 | SCNACs Virtual Update Meeting with Deborah Sturdy | Friday 17th January 2025 from 2.30-3.30pm. Reserve your free ticket here: | https://www.eventbrite.co.uk/e/social-care-nursing-advisory-councils-where-are-we-now-tickets-1113668224639?aff=oddtdtcreator | The OS | 2025-01-17 |  | 2025-01-17
2024-10-01 | Weekly CNO Meeting | Ask for a slot at one of their meetings - ask for support | Lynn to ask for a slot at a future meeting. | Anita / Lynn Tolly | 2024-11-14 | Anita and Jo-Anne to meet Regional CNOs on 14-Nov-24 at 15.00 hours virtually. | 2024-11-14
2024-10-01 | Presentations | Katie and Shirley to send theirs over | Katie Welborn presented her bid for a Social Care Academy. | Katie/ Shirley | 2024-10-02 | Establishing a Social Care Academy is one of our two priorities. Attached with action points | 2024-10-02
2024-07-02 | Benchmarking | Anita is in talks with NIHR to see whether benchmarking is something we could take forward across the Midlands. Will keep the group updated. | Anita was able to do a benchmarking initiative, which was LPZ and led to quality improvement. From the initiative the number of things that were able to change for the people living in our care home through doing benchmarking and comparing with other care homes was immense until Academic Health Science Network lost the funding. Katie would be happy to be involved in this. | Anita | As available | 20 Aug 24 Discussions continue. 01-Oct-24 This has been incorporated into one of our regional prioritie - Digital Social Care - benchmarking to support quality improvement. Zena Aldridge is a member of our working group. This item is marked completed. | 2024-10-01
2024-07-02 | Draft Terms of Reference (TOR) | Consider the points brought up | Jackie: Re-Quoracy - this should be very much more working in adult social care. No disrespect to all the wonderful expertise we have on here but to keep on track with the original principle the quoracy needs to include the actual people doing the caring - maybe 50% of the 10? So 5 from direct adult social care. Tony: NMC is not listed on the ToR (see update) | Anita/Jo-Anne | 2024-10-01 | 02Jul24 At least 6 people on the meeting agreed that there should be a minimum of 5 people from direct adult social care at each meeting 12Jul24 - NMC not being listed was a complete oversight and has been updated on all regional ToR. 01Oct24 - Made tweaks, revised and shared - no comments back - fine to share on website. | 2024-10-01
2024-07-02 | MSc Community Specialist Practice Qualification (SPQ) in Health and Social Care | MSC has been developed for specialist practise with University College Hospital, Birmingham that has NMC approval. | Louise to share information with the group. Looking for providers to send people on this course, starting in September and there are various routes for funding. | Louise | ASAP | Information available on the website | 2024-07-02
2024-07-02 | Shropshire, Telford & Wrekin area | Update membership list as Alison Bussey has retired and has been replaced with Vanessa Whatley |  | Sonia | 2024-07-12 | Done | 2024-07-12

## Updates and Information
NAME OF GROUP: MIDLANDS Region Social Care Nursing Advisory Councils (SCNACs) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-07-22 | Skills for Care - Nursing placement strategy launch event: Social care as a nursing placement of choice Wednesday 23 July 2025 ¦ 10:00 – 11:00 ¦ Online | Skills for Care in partnership with the Council of Deans Health is launching the first ever placement strategy for social care nursing. Join us for this online launch event to learn more about the strategy and how social care can become a placement of choice for all student nurses and nursing associates. Key speakers include Stephen Kinnock MP, Deborah Sturdy - Chief Nurse for Adult Social Care, Tristram Gardner - Deputy CEO Skills for Care and Ed Hughes - CEO Council of Deans of Health. | This online event will bring together social care nursing, social care providers, universities and colleges to hear about the placement strategy and how they can implement it in social care and education across England. https://www.skillsforcare.org.uk/news-and-events/Events/July/Social-Care-as-a-Nursing-Placement-of-Choice.aspx | Skills for Care | 2025-07-23
2025-05-07 | Quarterly Insights with the CQC - FREE Virtual Event | Shared in the chat: | https://www.eventbrite.co.uk/e/quarterly-insights-with-the-cqc-tickets-1255506266039?aff=ebdssbdestsearch | The OS | 2025-05-15
2025-05-07 | Adult Social Care Nursing MSc - Postgraducate Courses | Shared in the chat: | https://www.ucb.ac.uk/study/courses/postgraduate/community-spq-in-health-and-social-care-adult-social-care-nursing-msc/ | Louise Luckman | For Reference
2025-05-07 | NIHR Researcher Development Programme for Social Care Nurses | Shared in the chat: You can apply for funding to work on research for 1 day a week for a year for: Social Care Nurse Research Internships - 12 places available Social Care Nurse Research Champions - 24 places available | https://www.nihr.ac.uk/researcher-development-programme-social-care-nurses |  | For Reference
2025-05-07 | RCN Infection Prevention and Control for People Working in the Independent Health and Social Care Sector Event | Shared in the chat: Also open to non-members | https://www.rcn.org.uk/news-and-events/events/wm-ihsc-webinar-200525 | Samantha Preston | 2025-05-20
2025-05-07 | RCN Nursing Adults Towards the End of Life | Shared in the chat: Also open to non-members | https://www.rcn.org.uk/news-and-events/events/uk-nursing-adults-towards-the-end-of-life-in-the-independent-health-and-social-care-sectors-280525 | Samantha Preston | 2025-05-28
2025-05-07 | Skills for Care National Nurses Day Event on Monday 12May25 | Shared in the chat: | https://www.skillsforcare.org.uk/news-and-events/Events/May/International-Nurses-Day-2025-event.aspx#:~:text=This%20year%2C%20the%20International%20Council,better%20outcomes%20for%20communities%20worldwide.
2025-01-17 | SCNAC Progress and Impact 6 months on | If you were not able to make our virtual progress meeting in January, you can listen again here: | https://www.youtube.com/watch?v=7qa5APv9BIw&t=3s | SCNACs | For Reference
2025-01-14 | Social Care Birmingham & Solihull Training Hub | Shared in the chat: | https://sdstraininghub.co.uk/social-care/ |  | For Reference
2025-01-14 | Digital Space: Microsoft Free Training for Women in Health and Social Care 'Tech Her' | Shared in the chat: | https://digitalcarehub-my.sharepoint.com/personal/katie_digitalcarehub_co_uk/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkatie%5Fdigitalcarehub%5Fco%5Fuk%2FDocuments%2FMicrosoft%20Teams%20Chat%20Files%2FTechHer%20Health%20and%20Social%20Care%20Flyer%2Epdf&parent=%2Fpersonal%2Fkatie%5Fdigitalcarehub%5Fco%5Fuk%2FDocuments%2FMicrosoft%20Teams%20Chat%20Files&ct=1736867884736&or=Teams%2DHL&ga=1 | Katie Thorne | For Reference
2025-01-14 | Skills for Care Midlands Regional Conference - 05Feb25 in Birmingham | Still a few places left: | https://www.skillsforcare.org.uk/news-and-events/Events/February/East-and-West-Midlands-regional-conference-–-moving-forwards.aspx | Shirley Way | For Reference 05-Feb-25
2025-01-14 | Digital Care Hub Ethical AI in Social Care | Shared in the chat: Not nursing specific, but Digital Care Hub have published their co-produced framework for ethical AI in Social Care: | https://www.digitalcarehub.co.uk/ai-and-robotics/oxford-project-the-responsible-use-of-generative-ai-in-social-care/ethical-principles-for-the-use-of-ai-in-social-care-contexts/ | Katie Thorne | For Reference
2025-01-14 | NMC Employer Link Advisor (Midlands) | Shared in the chat: | https://jobs.theguardian.com/job/9424398/employer-link-advisor-milands-?utm_source=EmailAFriend&utm_medium=email&utm_campaign=9424398
2025-01-14 | Skills for Care new national forums: Nursing education forum | Shared in the chat: Skills for Care has established a new national social care nursing education forum focusing on NMC approved education programmes for nurses and nursing associates. This forum is for stakeholders involved in the delivery of nursing education and sessions will focus on social care in practice learning and in the nursing curriculum. | By attending the forum you will: • hear from others working in nursing education who are investing in the value of social care to support their learners • receive updates about the sector that will be relevant to nursing programmes • have a platform to share good practice, collaborate and network with other social care nursing stakeholders • debate issues and raise challenges for discussion with the forum. The next forums will be on Wednesday 22 January and Wednesday 19 March 2025 and are being delivered in collaboration with the University of Wolverhampton. If you’re interested in joining the forum please complete the expression of interest form and email it to SocialCareNursing@skillsforcare.org.uk | Shirley Way | 22-Jan-25 and 19-Mar25
2025-01-14 | Skills for Care new national forums: Nursing workforce forum | Shared in the chat: Skills for Care has established a new national social care nursing workforce forum to support attracting, retaining and valuing the social care nursing workforce across the sector. If you’re involved in supporting the development of the nursing workforce to include registered nurse and nursing associate roles, come and join us. | By attending the forum you will: • hear from others working across the system about issues relevant to nursing in the sector • receive updates, information and opportunities relevant to the social care nursing workforce • have a platform to share good practice, collaborate and network with other social care nursing stakeholders • debate issues and raise challenges for discussion with the forum. The next forums will be on Thursday 23 January and Wednesday 26 March 2025. If you’re interested in joining please complete the expression of interest form and email it to SocialCareNursing@skillsforcare.org.uk | Shirley Way | 23-Jan-25 and 26-Mar-25
2025-01-14 | Skills for Care Staffs/Stoke Academy | Shared in the chat: | https://youtu.be/5f6az4XF-hE http://www.staffsstokecareacademy.co.uk |  | For Reference
2024-10-01 | Social Care Nurses 'Critical' - NT Article | For Reference | https://www.nursingtimes.net/news/social-care/social-care-nurses-critical-to-incoming-healthcare-overhaul-12-09-2024/ | All | For Reference
2024-10-01 | SCNACS Celebration Event - 12th September 2024 | For Reference | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ | All | For Reference
2024-09-23 | Skills for Care Event: The adult social care sector and workforce in Central and Eastern England 2024 Tuesday 12th November 2024 from 10.00am-11.45am on Zoom | Each year, we produce important insights about the adult social care workforce on a national, regional and local level. These insights are used to inform planning, funding and decision making across the sector. In October we will be launching our latest State of the adult social care sector and workforce in England report along with new regional data. At this event you will hear the headline findings from your regional data and what they mean for you - including the size and structure of the workforce, recruitment and retention trends, local workforce demographics, pay and training. You will also hear how the data is used to inform workforce planning and how you can access and use our data throughout the year. This event will be looking specifically at the data from the: • West Midlands • East Midlands • Eastern region During the session delegates will be invited to join breakout rooms to hear further information about the data relevant to the area that they are located in. | Shared by Shirley Way from Skills for Care (Shirley.Way@skillsforcare.org.uk) https://events.skillsforcare.org.uk/skillsforcare/frontend/reg/thome.csp?pageID=644428&eventID=2003&traceRedir=2 | All | 2024-11-12
2024-07-02 | Midlands Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/scnac-midlands-region/ | All | For Reference
2024-07-02 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference | 01-Oct-24 - New data will be released by Skills for Care next week. We are forming a working part to look at this data and we hope to form a Social Care Academy to address our Workforce needs.
2024-07-02 | Skills for Care 'We are Social Care Nurses' Resources | Shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Nursing.aspx | All | For Reference
2024-07-02 | BSOL Social Care Nurses Network | Shared by Lucy Luckman in the chat | https://www.wmca.care/networks/nurses | All | For Reference
2024-07-02 | Skills for Care - Workforce Intelligence - Nurses in Social Care | Shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Adult-Social-Care-Workforce-Data/Workforce-intelligence/publications/Topics/Nurses-in-social-care.aspx | All | For Reference
2024-07-02 | Skills for Care - Join the Nursing Community | Link shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Join-the-nursing-community.aspx | All | For Reference
2024-07-02 | Valuing Social Care in Nursing Education: Emphasising the Narratives and Experiences of Social Care in Pre and Post Registration Nursing Programmes. | Shared in the chat: Some of you may be interested in attending this Skills for Care event which is being held on Thursday 18 July 2024 ¦ 09:30 - 15:30 ¦ University of Salford - Greater Manchester | Skills for Care is partnering with the University of Salford to explore the value of social care in nursing education. We know from the NMC that both pre-registration nurses and nursing associates should be able to work in any setting at point of qualification, yet the presence of social care placements and programme content means that for some students social care is misunderstood and undervalued. To book on - Valuing social care in nursing education (www.skillsforcare.org.uk) | All | 2024-07-18
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy | All | For Reference |  | 2024-06-19