## OPEN
NAME OF GROUP: MIDLANDS Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-02 | Draft Terms of Reference (TOR) | Consider the points brought up | Jackie: Re-Quoracy - this should be very much more working in adult social care. No disrespect to all the wonderful expertise we have on here but to keep on track with the original principle the quoracy needs to include the actual people doing the caring - maybe 50% of the 10? So 5 from direct adult social care. Tony: NMC is not listed on the ToR (see update) |  |  | 02Jul24 At least 6 people on the meeting agreed that there should be a minimum of 5 people from direct adult social care at each meeting 12Jul24 - NMC not being listed was a complete oversight and has been updated on all regional ToR.
2024-07-02 | Additional Members | Review list of key, inspirational, motivated, dedicated infulential managers that want to be part of the group sent to Anita by Louise Luckman in May 2024 | Louise will resend email to Anita (chair.midlands@scnac.co.uk) is happy to make introductions | Louise / Anita | ASAP
2024-07-02 | Gaps in Memberships | Aim to make sure that no ICB footprint is left untouched or unrepresented | 14.Birmingham & Solihull - Louise Luckman 15.Black Country & West Birmingham - Katie Wellborne 16.Coventry & Warwickshire - new CNO in post 17.Joined Up Derbyshire - CNO vacancy 18.Herefordshire & Worcestershire - Kathryn Cobain 19.Leicester, Leicestershire & Rutland - Kay Derby 20.Lincolnshire - Tony Vine 21.Northamptonshire - Gabriella Okeeffee 22.Nottingham & Nottinghamshire - Diane Kareen Charles 23.Shropshire, Telford & Wrekin - Vanessa Whatley 24.Staffordshire - Becky Scullion Represented at the meeting in black / Not represented at the meeting in red | Anita / Jo-Anne | Ongoing
|  | Need: Supported Living Organisation Domiciliary Care Representation Early Careers Nurse Residents | If anyone has suggestions of people to approach, please make the appropriate introductions to Anita (chair.midlands@scnac.co.uk) and Jo-Anne (co-chair.midlands@scnac.co.uk) | All | ASAP
2024-07-02 | Local Priorities | National priorities have been adopted (see updates and information), as a region we need to adopt one or two local priorities that sit comfortably across all of our ICBs | See some of the suggestions given in the Attendance Document Please submit your suggestions to us and we might send out a poll.
2024-07-02 | Extending the Nursing Network | Shirley suggested looking at this with Louise and Lucy |  | Louise / Lucy / Shirley
2024-07-02 | Social Care Nursing Advisory Council (SCNAC) | Create more awareness about SCNAC among social care nurses. | This might help to attract more involvement.
2024-07-02 | Good News Stories | Rights for Residents are about to ask their appox. 8000 members to share their good news stories and Diane will share accordingly |  | Diane | When available
2024-07-02 | NMC - International Nurses - Welcome to the UK Workshop | Workshop has been developed by NMC over the last year. If you would like more details please let us know and we can put you in touch with Tony Newman | Designed and aimed directly at international nurses to talk to them about some of the ethical and cultural changes and differences they will experience practising in the UK. Been rolled out to ICB's and trusts, but equally it should be offered to the Social Care network as well. | All / Tony | As required
2024-07-02 | Prescribing | Katie is exploring from a governance perspective in terms of prescribing, how they migrate or expand what we're already doing in primary care? | If we can do it in primary care, why can't we do it in the independent sector if we've got an overarching governance framework that is there to support the growth through the business Academy? Will bring back to the group her findings. | Katie | When complete
2024-07-02 | Council Members Bios and Photos | Please submit your high resolution photos and short bios (approx. 100 words) to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to be included on the website | Would be grateful if you could put 'Midlands' in the subject line | All | ASAP
2024-07-02 | Website Content | Please share good news stories and examples of best practice and we will add these to our webpage (including care awards, winners, finalists from your areas) | Again please forward any stories to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) and put 'For Midlands Webpage' in the subject line | All | As available
2024-07-02 | Communication | Everyone on the call was happy for the group to communicate through email. If any has any communication suggestions - either a Whats App group or a facebook page, please send across your suggestions to Anita and Jo-Anne.
|  | Suggestion to set up a Midlands Network for Nurses or possibly tap into/promote an existing group | Lucy McDonald at Skills for Care has recently set up a What's App group for Social Care Nurses. Could this be regional? Tom suggested it should NOT be on What's App There will also be a secure area on the website that is currently being developed. | Anita / Jo-Anne / Shirley (Skills)
|  | Please forward any suggested agenda items / items for discussion at the next meeting to Anita and Jo-Anne | Anita - chair.midlands@scnac.co.uk Jo-Anne - co-chair.midlands@scnac.co.uk | All | Before next meeting
2024-07-02 | Registered Managers Posts | Provide Skills for Care figures on this to the group |  | Shirley | As available
2024-07-02 | Benchmarking | Anita is in talks with NIHR to see whether benchmarking is something we could take forward across the Midlands. Will keep the group updated. | Anita was able to do a benchmarking initiative, which was LPZ and led to quality improvement. From the initiative the number of things that were able to change for the people living in our care home through doing benchmarking and comparing with other care homes was immense until Academic Health Science Network lost the funding. Katie would be happy to be involved in this. | Anita | As available

## Complete
NAME OF GROUP: MIDLANDS Region Adult Social Care Engagement Collective (ASCEC) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-02 | MSc Community Specialist Practice Qualification (SPQ) in Health and Social Care | MSC has been developed for specialist practise with University College Hospital, Birmingham that has NMC approval. | Louise to share information with the group. Looking for providers to send people on this course, starting in September and there are various routes for funding. | Louise | ASAP | Information available on the website
2024-07-02 | Shropshire, Telford & Wrekin area | Update membership list as Alison Bussey has retired and has been replaced with Vanessa Whatley |  | Sonia | 2024-07-12 | Done | 2024-07-12

## Updates and Information
NAME OF GROUP: MIDLANDS Region Adult Social Care Engagement Collective (ASCEC) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-02 | Midlands Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/scnac-midlands-region/ | All | For Reference
2024-07-02 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference
2024-07-02 | Skills for Care 'We are Social Care Nurses' Resources | Shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Nursing.aspx | All | For Reference
2024-07-02 | BSOL Social Care Nurses Network | Shared by Lucy Luckman in the chat | https://www.wmca.care/networks/nurses | All | For Reference
2024-07-02 | Skills for Care - Workforce Intelligence - Nurses in Social Care | Shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Adult-Social-Care-Workforce-Data/Workforce-intelligence/publications/Topics/Nurses-in-social-care.aspx | All | For Reference
2024-07-02 | Skills for Care - Join the Nursing Community | Link shared by Shirley Way in the chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Join-the-nursing-community.aspx | All | For Reference
2024-07-02 | Valuing Social Care in Nursing Education: Emphasising the Narratives and Experiences of Social Care in Pre and Post Registration Nursing Programmes. | Shared in the chat: Some of you may be interested in attending this Skills for Care event which is being held on Thursday 18 July 2024 ¦ 09:30 - 15:30 ¦ University of Salford - Greater Manchester | Skills for Care is partnering with the University of Salford to explore the value of social care in nursing education. We know from the NMC that both pre-registration nurses and nursing associates should be able to work in any setting at point of qualification, yet the presence of social care placements and programme content means that for some students social care is misunderstood and undervalued. To book on - Valuing social care in nursing education (www.skillsforcare.org.uk) | All | 2024-07-18
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy | All | For Reference |  | 2024-06-19