## OPEN
NAME OF GROUP: NORTH EAST & YORKSHIRE Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-09-26 | Monthly Update | Monthly update to all members on what is going on with other councils. | Everyone can kow what is happening outside working groups. Let Anthony/Karen know if you are not happy for email address provided to be shared. Should be work/professional email addresses | Anthony / Karen Roberts | Ongoing
2024-09-26 | Front Line Voices | Explore and look at - set up working group. | Link with other key stakeholders for other action groups. Michelle R and Kristian to be part of working group. Rory and Leanne H happy to be part of delegated activities group. Simon Hill key member to look at. Julie and Gill will take on working group with priorities. | Anthony / Karen Roberts | ASAP
2024-09-26 | Initial Meeting for Workstreams | Short term goals to be established. Top 10 delegated tasks. Measurable outcomes to be identified. | Cathy W happy to support. Need to link in with frontline staff. Cathy has social care nursing group - is an SRO for. They have workstreams. | Karen | ASAP
2024-09-26 | Ideas on Overall Objectives | What achievement of outcomes would look like, any burning areas? | Clarity on financial implications of delegated activity. How regularly delegated competencies are reviewed. Preventing delayed discharge. Getting providers trained. Skills for care working on. Acute health should be able to help. David can also support. Having help from acute sector regarding competency checks. Michelle - Hot topic would be continence assessment and support | Anthony
2024-09-26 | Sharing Stories | Sharing stories, case studies, blogs, research of exemplary stories and work done. | If people have links to others that will be good, let Anthony know. Look at barriers and how people have got around them, and working with NMC. Signpost people to share. | Anthony
2024-07-12 | Terms of Reference (ToR) | If no amendments requested, draft ToR will be adopted and uploaded to our webpage | Clarify in ToR that any recordings are for note taking purposes. NMC are not included on the membership list? | All | 2024-08-30 | 12Jul24 - The omission of NMC was an oversight from all regional ToR and this has been updated. NMC are on the membership list.
2024-07-12 | Gaps in Membership | Looking for council members to represent Cumbria. Consider reserch fellowship or NIHR with Social Care focus. | Please make any relevant introductions to Anthony and Karen
2024-07-12 | Delegated Healthcare | When available Karen will share the work that Skills for Care have done. | Currently DHSC funded work is at a standstill due to the election and they are waiting for the timeline | Karen Morse | When published
|  | Suggest possible working group / task and finish group to have further conversations outside of the council, once Skills for Care are moving forward again and report back | Suggest Karen Morse, Jo and Rory | Karen Morse / Jo / Rory | When appropriate | Tameside have successful framework - Speak to them and get details on this
2024-07-12 | Website Content | Each member of the council to submit (or link to someone that can submit) a story to showcase a practise, an event, a process you have implemented to highlight Social Care, Nursing, Adult Social Care, to be uploaded to the website. | Signposting to resouces. Sharing really exemplary innotive practise that goes on in Social Care. Submit to Anthony (chair.northeastandyorkshire@scnac.co.uk), Karen Roberts (co-chair.northseastandyorkshire@scnac.co.uk) and Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) | All | Before the next meeting
|  | Section to share training opportunities, funding opportunities (nationally and regionally) Also key messages - what we are doing, what progress we are making and what we are talking about |  | All | As available
|  | Council members - Photos and Bios | Bios approx. 100 words. Sent to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) and please put North East & Yorkshire in the subject. Email addresses won't be added unless you specifically ask for them to be. | All | ASAP | Still ongoing - Put North East and Yorkshire in the subject when sending.
|  | Key organisations in the region. Complie a list. Please forward any thoughts of key organisations through to Anthony and Karen | Example of what is required will be attached to the action points. | All | To be discussed at the next meeting
2024-07-12 | Regional Website | Please do signpost everyone to our webpage | Link can be found on the Updates and Information tab. Please share far and wide. | All | Ongoing
2024-07-12 | Social Care Placment Expansion | RCN currently have a project workin gon Social Care Placement Expansion - Universities are part of the collaborative work. Leanne happy to share this. |  | Leanne | When possible
2024-07-12 | Running Question | Suggest that each meeting we ask oursleves are we reaching all of the individuals on the ground and how are we making sure that our messages are getting out? | Add regional communication plan to the agenda for the next meeting | Anthony / Karen Roberts | Next Meeting
2024-07-12 | Local Authority | Make contact with local authority and local care associations to enable us to tap in to their commuication with Providers. Suggest link to SCNAC webpage. Utlise networks that are already up and running. | If anyone has introductions they can make to Anthony and Louise, please do so. | Anthony / Karen Roberts
2024-06-12 | The Curiosity Partnership | Research a mutual link
2024-06-12 | Access tro training for certain elements of clinical skills | Doing piece of work in North Yorkshire - Nicola to share updates |  | Nicola | As available

## Complete
NAME OF GROUP: NORTH EAST & YORKSHIRE Region Social Care Nursing Advisory Councils (SCNACs) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-12 | Recordings of Quarterly Meetings | Clarify if the meetings will be uploaded to the website |  | Anthony | ASAP | Meetings are recorded for note taking purposes only but can be available to the Chairs/Co-Chairs for reflection if required | 2024-07-15

## Updates and Information
NAME OF GROUP: NORTH EAST & YORKSHIRE Region Social Care Nursing Advisory Councils (SCNACs) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-09-26 | Driving Change | Facilitating increased placements | Michelle Carrington - Courses that have been developed for nurses. Nicola - In York they have developed partnership agreement with two local universities to expand placements. Cathy also working on placement expansion in SY. David Purse - Has good examples of expansion in NENC - Uni now has a masters programme for social care advanced practice.
|  | NMC Regulated Advance Practice - Shared in the chat: | https://www.nmc.org.uk/about-us/our-role/advanced-practice-review/ |  | For Reference
|  | Specialist Practice Qualification -Shared in the chat: | https://www.northumbria.ac.uk/about-us/news-events/news/northumbria-launches-uk-first-specialist-practice-qualification-in-adult-social-care/ |  | For Reference
2024-09-26 | Accountablity and Delegation | Shared in the chat: | https://www.rcn.org.uk/professional-development/accountability-and-delegation |  | For Reference
2024-07-12 | North East & Yorkshire Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/north-east-yorkshire-region/ |  | For Reference
2024-07-12 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference
2024-07-12 | NMC Resources | In January 2024 NMC announced that they would be commissioning research into nursing and midwifery students’ practice learning requirements. To sign up for updates: | https://r1.dotdigital-pages.com/p/129A-1B4W/practicelearning |  | For Reference
2024-07-12 | Skills for Care - Person Centred Delegation of Healthcare Activities | Shared in the chat: | https://www.skillsforcare.org.uk/news-and-events/news/guiding-principles-developed-to-support-person-centred-delegation-of-healthcare-activities-to-care-workers |  | For Reference
2024-07-12 | Skills for Care - Practicalities of Delegated Healthcare Activities | Shared in the chat: | https://www.skillsforcare.org.uk/Support-for-leaders-and-managers/Managing-a-service/Delegated-healthcare-activities/Delegated-healthcare-activities.aspx |  | For Reference
2024-07-12 | RCN Accountability and Delegation | Shared in the chat: | Accountability and delegation ¦ Royal College of Nursing (rcn.org.uk) Accountability and delegation ¦ Royal College of Nursing It is vital that each member of the nursing team is clear about their level of accountability and that registered staff are confident when delegating tasks. |  | For Reference
2024-07-12 | Skills for Care - Registered Manager Network | Skills for Care has registered manager networks across the region - which includes nurses. We also have a recently established community of practice for nurses in social care - next meeting 23rd July if anyone is interested. | If interested please contact Karen Morse |  | For Reference
2024-07-12 | NMC Newsletter | NMC have newsletters for a range of stakeholders including students, stakeholders, employers and those on our register. Please share details with colleagues/networks - you can sign up here: | https://www.nmc.org.uk/news/email-newsletters/ |  | For Reference
2024-07-12 | Centre for Care | Shared in the chat: | https://centreforcare.ac.uk/ |  | For Reference
2024-07-12 | NIHR | Shared in the chat: | https://www.nihr.ac.uk/ |  | For Reference
2024-07-12 | NIHR - The Curiosity Partnership | Shared in the chat: | https://www.curiositypartnership.org.uk/about/ |  | For Reference
2024-07-12 | Health Innovation Network | Shared in the chat: | https://thehealthinnovationnetwork.co.uk/ |  | For Reference
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' | For Reference | https://thehealthinnovationnetwork.co.uk/ |  | For Reference