## OPEN
NAME OF GROUP: NORTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-09-24 | Review Date | 1.Need a review date organised for members for next year. | Karen suggested July 2025, to be confirmed | Karen | 2025-07-31
2024-09-24 | National Priorities - Education and Workforce - Being Student Ready | 2.Education of pre-registered nurses. Making the social care sector 'student ready' and building a space to share. Myth busting out on placements and thinking about where the next cohort of students will come from. Social care being a mandatory placement for students. | Sue Noon expressed interest. She has just started welcome packs for students and will share with everyone for them to also pass to other regions. Melanie Stephens and Liz Williams also expressed interest in the chat. | Melanie Stephens / Liz Wiliams/ Sue Noon | ASAP
2024-09-24 | ICB pot of funding | 3.Find out which pot this is so people can reach out. | Liz Williams mentioned Dawn Wearer for funding, and seeing if she can come along next time. Emma OKane will find the email regarding funding she has and share this | Liz Williams/ Emma Okane | ASAP
2024-09-24 | Inspiring Module | 4.Melanie uses a module called Inspiring, and has got care home managers to be a part of. Karen mentioned developing sub committees and working groups for this. Putting out a call to arms to plug any gaps. | Melanie has a meeting also regarding this. she invited the group to contact her . | Melanie / Karen | Nov end
2024-09-24 | Developing Student Placements - Medical Outreach Programmes | 5.Event coming up where people will share the learning from this | Find out and send the link for this - November 18th. Andrea Boland to be invited (andera.boland@nhs.net) to the meeting to give update on Regional WT&E work and supporting next steps. | Michelle Howarth | Oct end
2024-09-24 | NW Merseyside Examples - Day In the Life Of | 6.With their permission we can use these to reach out to education providers to utilities this with storytelling. Developing communication pieces and flyers for this. | Melanie created a survey and scale for ICB project asking students week by week what they have learnt about themselves. Can we develop this further as data | Sue Noon | Nov End
2024-09-24 | Student Experiences | 7.Student experiences - and why they came back to the workplace they had placement at one qualified. | Emily Devitt - From a base level noticed students were not getting external placements and contacted local universities to ask why. Reaching out to those universities. If placements are cancelled within NHS, putting yourself out there so you are contacted. Feedback available also on SCTH website and flyers (lscthub.co.uk) | Emily Devitt | Nov End
2024-09-24 | Workshop - Internationally Trained Nurses | 8.To help with transitions. | Get in touch with Mark Brooke or Paula - regulation advisor for NW regarding this. | Mark Brooke/ Karen Davies/All educators | Oct end
2024-09-24 | Engaging and Building Relationships with NWAS | 9. More cohesive relationships. Michelle and Karen will feed back. Potential to reduce unnecessary referrals to safeguarding teams. Clinical understanding - how we work and communicate as a profession to reduce misunderstandings on what is reported. Very different safeguarding criteria to social care, Catherine Brierley would be happy to work on NWAS as has been at this for years. Working to improve understanding between professions. | Understanding safeguarding training paramedics get. Where the gaps are we can work towards with them. Emma O'kane has a link to a TED talk on civility and can share this. Melanie said this was an issue with care homes that comes frequently and would like to be involved in this too. Emma to share information with the group . Jacke offered help also with NWAS as had had conversations with them. Emma Okane referenced Angela Clarke re Safe transfers of care - workstream- NWAS involved will provide link ups. Andrea Boland was invited to the next meeting by Jackie Hanson | Karen/Catherine/Emily/ Emma/ Melanie/ Jackie | Ongoing- Acton specific meeting TBA by Oct end
2024-09-24 | Paramedic Programme - Edge Hill | 10.The only nurse paramedic programme - to understand concept. Has first cohorts going through. They have invited a student to the January meeting to see what they have learned and their relationship with social care. To explore some challenges that Karen mentioned. Where did they go after the placements. | Put any questions to Karen for the guest speakers in January. | Michelle | Nov end
2024-09-24 | Website Content | 11.Share good stories & best practice so that we can in turn share them on our webpage. Could some of the excellent good practice going on be shared at the start of the next meeting? Can we share this on our website as a knowledge exchange? Sharing good practice through Karen and Michelle - to be shared on Outstanding Society website. Talk about challenges faced and how we will solve these. | Need to tell stories about the residents, experiences of the students, experiences of the care staff, nurse experiences. Invite people who are leading this this area to come and talk about their work to inspire and influence the discussion | All | Ongoing
2024-07-11 | RCN & Activist Academy | RCN are doing work with the Activist Academy. If you want to become more active, please connect with Melissa Stanton |  | All / Melissa Stanton
2024-07-11 | Terms of Reference (ToR) | If no amendments requested, draft ToR will be adopted and uploaded to our webpage. Pay special attention to section 9 - Core Values by Which we Work (or Ways of Working.) If there is anything you would like to add, please let us know. | Suggestions from Michelle 'Being impactful so that its not just a talking shop - what can we take forwards from this meeting?' maybe worded as 'Be honest in your committments'. How we disseminate and act to enable a safe environment that will enable discussion and actions that make a difference to social care nursing. Being solution focused. To make a difference for residents. Regional meeting fights for what is best for our area within the bigger national arena. Commit to actions that are achieveable. | All | 2024-08-16
|  | Confidentiality and information sharing | What is discussed at the meeting may be shared with the nationals SCNACS. This is a safe space so we need to feel comfortable to be able to say, I'm happy to share in this space, but do not want what I am saying to be shared further or referenced in the minutes | All
2024-09-24 | Gaps in Membership | 12. Please come back to Karen or Michelle if you feel there are gaps in your areas / your field / your discipline, and we can discuss those at the next meeting. | Thinking about passionate students who could represent themselves in the sector. Consider who is round the table - who is in the finishing groups and the meetings, identify people to fill the gaps - to be the megaphone for social care users. RCN was coming back with disability members at some point. Sue Noon - has a student in mind. Melanie Stephanie - Recommended Jacob who she will ask. | Sue / Melanie / All | ASAP but before next meeting
2024-07-11 |  | Identifying gaps - if you feel something is missing and if you have contacts who would be keen, passionate and willing to join, please make introductions. | Students are missing, post-reg and pre-reg LD (Learning Disability), MH (Mental Health, Homeless and Public Health. Residents. Admiral Nurses QNI (Queen's Nursing Institute). Prisons. CQC. | All | End July
|  | Barbara has lots of newly qualified and promoted from training - please let her know if you would would like an introduction. |  | Barbara / Karen | If required
|  | Melanie knows some very inspiring LD nurses who are doing amazing, incredible work, as well as nurses in other areas and can make introductions |  | Melanie / Karen | ASAP
2024-07-11 | Preceptorship | Currently trying to implement preceptorship in Cheshire & Merseyside and its proving more difficult than they thought. Happy to feedback more at the next meeting | Could bring Kathy, Designated Social Care Perf(?)
2024-07-11 | Understanding the Pathways and Mechanisms to Support Students to Engage Across a Range of Sectors. | This was a piece of work that Michelle woked on in March 2023 and she will share the report if anyone is interested | Report identiries potential opportunities for streamlining funding. | Michelle
2024-07-11 | Newsletters | If not already signed up, details of how to sign up to the NMC and Skills for Care newsletters are on the Updates and Information tab - but suggestion to submit some guest articles around SCNACs. Paula to put Karen in touch with the NMC Communication Team and perhaps Jez could do the same. | Opportunities to showcase some of the good practice going on in the region / sector and also maybe something around encouraging students to consider the sector as opposed to NHS. | All / Paula / Jez / Karen | As appropriate
2024-07-11 | NMC Support | If there any suggestions or support that people want from the NMC directly, please reach out to Loucia or Paula | If you contact Sonia (Admin.SCNAC@theoutstandingsociety.co.uk), she will be able to put you in touch | All | As required
2024-07-11 | Claire Pryor's new post | Can we invite her to a future meeting | Claire is starting her new post at Salford on 31st July as the first chair in Social Care | Karen / Michelle |  | Claire will attend to monthly SCNACs meetings in order to feedback to all Chairs/Co-chairs in all regions.
2024-07-11 | Championing the Sector | Consider who might champion the cause? Suggestions welcome. | We have 2 mayors in the Liverpool and Greater Manchester area - use them to champion the sector and influence what what might be our focus, aims and aspirations for Social Care and Social Care Nurses.
2024-07-11 | Challenge | In the Northwest or in any of the areas would we ever consider adopting a quota style or a commitment to a percentage of hours placement for student nurses in the future? |  | Karen

## Complete
NAME OF GROUP: NORTH WEST Region Adult Social Care Engagement Collective (ASCEC) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-11 | Local Priorities | What should our local priorities be? Please submit your ideas | We will organise a poll with all of the ideas | All | 31-Jul-24 to be agreed at the next meeting | Adoped local priorities are: 1) Developing relationships for admissions avoidance 2) Ensuring social care is 'student nurse ready' | 2024-09-24
2024-07-11 | Terms of Reference (ToR) | NMC is missing from the membership | See update |  |  | 12Jul24 - NMC not being listed was a complete oversight and has been updated on all regional ToR. | 2024-07-12

## Updates and Information
NAME OF GROUP: NORTH WEST Region Adult Social Care Engagement Collective (ASCEC) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-09-24 | Cheshire & Merseyside Digital Newsletter for Student Placement Providers in the Social Care Sector | Newsletter forwarded by Sue Noon was attached to the email with the meeting action points. |  |  | For Reference
2024-09-24 | Funding to Support Nursing Apprenticeships 2024/2025 | The deadline for the funding Emma O'Kane had information on was Midday on Friday 31st May 2024 BUT contact included to point people in the right direction for further information of what is available. | Please contact Dawn.Werra@nhs.net if you would like support from the Social Care Training hub to enrol onto the apprenticeships mentioned in the funding guidelines. https://forms.office.com/pages/responsepage.aspx?id=slTDN7CF9UeyIge0jXdO48s8d514ZUVLkY3r8-squIJUODM4N1BMMUdKVDNQTzc4UkdNT1pGRkRGRSQlQCN0PWcu |  | For Reference
2024-09-24 | TED Talk on Civility | Shared in the chat by Emma O'Kane | When rudeness in teams turns deadly ¦ Chris Turner ¦ TEDxExeter - YouTube |  | For Reference
2024-09-24 | Lancashire and South Cumbria - Social Care Placements | Shared in the chat by Liz Williams | Social Care Placements – Lancashire and South Cumbria Training Hub (lscthub.co.uk) |  | For Reference
2024-09-24 | IPE Student Training Care Homes | Shared in the chat by Melanie Stephens | IPE Student Training Care Homes: A Longitudinal Study - Centre for Applied Health Research (salford.ac.uk) |  | For Reference
2024-09-24 | SCNACs Celebration Key Note Speaker | Major General Tim Hodgetts was the Key Note Speaker at our SCNACs celebration on 12th September | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ |  | For Reference
2024-07-11 | North West Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/north-west-region/ |  | For Reference
2024-07-11 | NMC - Review of Nursing and Midwifery Practice Learning | In January 2024 we announced that we would be commissioning researching to nursing and midwifery students’ practice learning requirements. If you’d like to keep up to date and be notified of future opportunities to get involved, please sign up to our community of interest. | https://r1.dotdigital-pages.com/p/129A-1B4W/practicelearning |  | For Reference
2024-07-11 | Principles of Preceptorship | Preceptorship is the structured start for newly registered nurses, midwives and nursing associates. See link for useful resources from the NMC. | https://www.nmc.org.uk/standards/guidance/preceptorship/ |  | For Reference
2024-07-11 | Funding | Shared in the chat by Barbara: Just a reminder of the RNDA for LD and top up from NA and AP (general and mental health) funding currently with ICB's. £8800 pa per student. |  |  | For Reference
2024-07-11 | NMC Newsletter | NMC Newsletters: You can sign up to receive any number of regular newsletters. Please note that our email newsletters may go into your ‘junk’ folder so I’d advise you save ‘info@nmc-news.org.uk’ to your safe senders list. | https://www.nmc.org.uk/news/email-newsletters/ |  | For Reference
2024-07-11 | Skills for Care Newsletter | If you aren't already signed up, you can sign up for the Skills for Care newsletter using the following link: | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Join-the-nursing-community.aspx |  | For Reference
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' | For Reference | https://vimeo.com/958966378?share=copy |  | For Reference |  | 2024-06-19