## OPEN
NAME OF GROUP: NORTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
08-Jan-25 Pinned | Council Members Photo and Bio for the Website | If you have not already done so already, please do send us a high resolution photo of yourself and a short bio (approx. 100 words) that we can upload onto the Northwest SCNAC page. | North West page can be found here: https://theoutstandingsociety.co.uk/north-west-region/ Photos and bios to: Admin.SCNAC@theoutstandingsociety.co.uk | All | ASAP
2025-07-23 | Chief Nurse Adult Social Care Awards | Deborah Sturdy is encouraging you all to please nominate colleagues and teams doing outstanding work for a Chief Nurse Adult Social Care Award. | https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms/chief-nurse-adult-social-care-awards-nomination-criteria | All | ASAP
2025-07-23 | Scoping Review | Working with RCN to develop a scoping review around preventable hospital admissions | Currently working with the RCN Research Institute and RCN library staff to develop the search strategy | Michelle | 12 months
2025-07-23 | Ensure student representation | Invite students to the NW SCNAC and (with agreement from Debs Sturdy and Lucy Gillespie) pilot a social care student nurses SCNACS champions scheme to compliment and work alongside the student ambassadors described in the Skills For Care Placement strategy. | Michelle to ask at EHU and Melissa Stanton will reach out to RCN Student COmmunity. | Karen & Michelle | Next meeting
2025-07-23 | Newly Qualified Practitioners Update | Email Jean Hales to request a summary statement about the plans for newly qualified practitioners to share with the SCNAC | James updated in the chat during the meeting that he had contacted Jean and she would be contacting the council via the OS and would directly contact Adele to answer her queries directly. | Michelle Howarth | ASAP
2025-07-23 | Preceptorship Programmes Information | Provide information on preceptorship programmes for Adult Social Care provision to support newly qualified nurses |  | James McLean | When Convenient
2025-07-23 | Preceptorship Webinars | Organise and promote a series of three webinars on preceptorships for social care providers |  | Carol | When Convenient
2025-07-23 | Develop a NW SCNACs Theory of Change Workshop | Organise a theory of change workshop to develop measurable outcomes and goals for the SCNAC | Sonia to coordinate a date for the ToC to take place. Michelle will facilitate | Karen & Michelle | 2025-02-26
2025-07-23 | Social Care Learning Environment Groups | Review progress on newly qualified nurses and preceptorship work in the autumn and plan next steps |  | Susan Clarke | Before next meeting
2025-07-23 | Social Care Placement Models | Expand the social care subgroup of the Northwest Practice Education Group to include HEIs and discuss future placement models |  | Susan Clarke | When Convenient
2025-07-23 | Ensure service user representation | To include a number of service users from across the sector | Carol Mitchell will reach out to SU groups in Skills for Care | Karen | Next meeting
2025-07-23 | Michelle Howarth's Commitment | To feedback from the role development and identify there is some work around looking at research. | Work with this group to develop those research priorities to feed that into that planning meeting in April online. | Michelle Howarth | Next meeting
2025-07-23 | Sarah Kennedy's Commitment | To look at all of the interesting things that people have been sharing and talking about. Would like to talk about her project that is coming to an end at the next meeting and share with Karen as part of what is going on in the region. | In particular reading the article that Sue and Sue were involved in writing. Writing up a resource to do with indirect practise supervision and assessment. | Sarah Kennedy | Before/at next meeting
2025-07-23 | Supporting Sarah Kennedy in her new role | Sarah to contact Carol Mitchell at Skills for Care when she has settled in to her new post to see how they can support | Sarah if you need Carol's contact details, please contact Sonia and she will put you in touch | Carol Mitchell / Sarah Kennedy | When in post
2025-07-23 | Training Package on Antipsychotic / Benzodiazepine Meds | NHS Lancashire and South Cumbria ICB are wokring on a training package - if any one has something already, please do share. | Please contact Sonia and she can put you in touch with Adele if you don't already have her contact. Susan Clarke to share some apps developed with Uni of GM that might be useful for format ideas (see updates and information). Julie York is interested to know more about this Adele. | Adele Thornburn / All | If available
2025-04-03 | Michelle Howarth's Commitment | To feedback from the role development and identify there is some work around looking at research. | Work with this group to develop those research priorities to feed that into that planning meeting in April online. | Michelle Howarth | Next meeting
2025-04-03 | Sarah Kennedy's Commitment | To look at all of the interesting things that people have been sharing and talking about. Would like to talk about her project that is coming to an end at the next meeting and share with Karen as part of what is going on in the region. | In particular reading the article that Sue and Sue were involved in writing. Writing up a resource to do with indirect practise supervision and assessment. | Sarah Kennedy | Before/at next meeting
2025-04-03 | Craig Priestly's Commitment | Meeting up with Barbara and Karen about the article for nursing older people. Meet up with Sue because of the Greater Manchester listening event activity coming up in May | Maybe at the next meeting he, Sue Clark and Sue Noon will hopefully have a kind of framework and be able to present those findings. | Craig | Next meeting
2025-04-03 | Sue Clarke's Commitment | As per Craig's commitment above, listening event is 15th May. Will circulate the invitation through this group incase people have not yet received invitations | Placements and curriculum and the learner pathway around social care. All welcome, particularly Care Home Managers. | Sue Clarke | 2025-05-15
2025-04-03 | Sue Noon's Commitment | Continue with the placements and curriculum work that she is doing in Cheshire, Merseyside - but also pushing on CPD for Social Care Nurses in her acute trust. | Will update at the next meeting | Sue Noon | Next meeting
2025-04-03 | Michelle Tennant's Commitment | To meet with NHS England regarding the student initiative. Working with delegated healthcare activities group on the competencies. Visiting the SCNAC stand at Care Show London Continuing work with pushing out the research and working with Skills for Care. | Already has six of her local fanchises with student placements so trying to push that out to a wider network. Will update at the next meeting | Michelle Tennant | Mtg booked 04-Apr-25 Mtg booked 30Apr/01May25
2025-04-03 | Paula Palmer-Charlery's Commitment | Comms colleagues are now hopefully ready to see if there areany people that can do some guest articles to raise the profile of all the great work happening and share the work. Going to send some of the links circulated during the meeting to colleagues who oversee independent adult social care work. | For reference, NMC have recently appointed several other advisors to the team who have a focus on engaging in independent sector and specifically adult social care, meaning there will hopefully be more to share as the months continue. | Paula Palmer-Charlery | Before next meeting
2025-04-03 | Peter Weller's Commitment | To work with Susan and Joe Finity in Greater Manchester to discuss adult social care placements and opportunities. | There some funding coming to an end and Peter is meeting with all of the provider chief nurses to look at whether theres and opportunity to coordinate something. | Peter Weller | Before next meeting
2025-04-03 | Pauline Bradshaw's Commitment | To share teh West Kent work around the single point of access hug with my regional UEC team as she is sure they are doing some similar work | The team might do some direct connecting in terms of some of the learning | Pauline Bradshaw | Before next meeting
2025-04-03 | Emily Devitt's Commitment | To speak to her nurses and get their feedback on the positives students bring to our service and how the barriers we have identified can be overcome from a floor nursing perspective, and what benefits they find. Also continuing to speak to students around their social care experience and changing perspectives. |  | Emily Devitt | Before next meeting
2025-04-03 | Melanie Stephen's Commitment | To send out CoP for NIHR such as ENRICH and Prison Nurses | So they can be shared and those interested can join. | Melanie Stephens | Before next meeting
2025-04-03 | Zena Aldridge's Presentation | Arrange for the presentation to be shared with NW Council Members |  | Michelle Howarth | When Obtained
2025-04-03 | Research Internships | Share the advert for the 12 regional social care nursing research internships |  | Michelle Howarth | Once Available
2025-04-03 | Research Champions | Invite locality-based social care nursing research champions to the next SCNAC NW quarterly meeting |  | Michelle Howarth | Jun-25
2025-04-03 | Listening Event | Circulate the invitation for the listening event on 15th May 2025 at Salford University to the SCNAC group |  | Susan Clarke | ASAP
2025-04-03 | Draft Placement Strategy | Will be closed for comments on 22nd April 2025. Jez to circulate the link to the draft document |  | Jez Ashdown | ASAP
2025-04-03 | RCN Foundation LV=Quality Improvement Project | Please share this widely. RCN Foundation have 10 grants of up to £2500 for quality improvement projects. Would be wonderful to have some social care ones. They have also opened up their education grants. | https://rcnfoundation.rcn.org.uk/Grants-and-funding/Research-and-practice-grants/RCN-Foundation-LV-Quality-Improvement-Project | Shared by Karen Davies | Open
2025-04-03 | CoP for NIHR | Melanie to circulate the CoP for NIHR such as ENRICH and Prison Nursese so they cna be shared and those interested can join. |  | Melanie Stephens | When convenient
2025-04-03 | Single Point of Access Hub | Presentation that was given during the meeting by Claire Bentley to be shared with the follow up | If there are any questions, please do send them to Sonia and we will get them answered for you | Sonia / All | Before next meeting
2025-04-03 | Action Points | Please read and share any updates or feedback from the action points by email to Admin.SCNAC@theoutstandingsociety.co.uk |  | All | 2025-04-30
08-Jan-25 / 03-Apr-25 | Ideas, Innovations, Solutions, Best Practise | If you have any.... please share. Either at the next meeting or inbetween. It might be a small thing - or it could be a huge solution for someone withing the sector so don't be shy! |  | All | Ongoing | 03Apr25 - we have not received any feedback from members to date so another rally cry for members to share what is going on - big or small!
2025-01-08 | Cavalry Healthcare Placement Opportunities | From the chat: Would love to offer placement opportunities within their services if there is an interest. | Cavalry Healthcare have had student nurses from Edghill before and there are lots of opportunities to see complex health needs. Contact Abbie Cliffe. | Abbie Cliffe | When required.
2025-01-08 | Nurse Paramedic Role Integration | Explore further with Health Education England and other partners how to develop and integrate the nurse paramedic role into the workforce, ensuring the job market is ready for this dual qualification. | Nurse Paramedic presentation included with email | Catherine Croughan
2025-01-08 | Research Opportunities | Contact Zena Aldridge to discuss how to maximize the opportunity for social care nursing research and potentially secure funding for research champions, internships, and pre-doctoral fellowships. | Discuss joint research opportunities with Zena and how they align with the RCN strategy | Michelle Howarth (copy Deborah Sturdy in to comms)
2025-01-08 | Digital Solutions for Care Homes | Follow up with Alice on the digital solutions for social care, particularly addressing the issue of rural broadband costs. |  | Deborah Sturdy
2025-01-08 | Funding for Nursing Associates | Provide feedback on the impact of the funding received for nursing associates and explore possibilities for additional funding. |  | Barbara
06-Dec-24 07-Jan-25 | Student ready | e meeting | Dr Nicky Morrell-Scott Nursing Workforce Senior Manager Nursing, Midwifery & Public Health Team Health & Care Education Sub-Directorate Workforce, Training and Education (WT&E) Directorate NHS England - NW - discussing placement readiness joining up NW initiatives - T levels - tarrifs blockers and solutions . to be NW member | Karen | ongoing
22-Nov-24 29-Jan-25 | Social Care Nursing Workforce & Education Group | NW workforce development priorities | identfied Student ready and access to education and enabling research opportunties | Karen Michelle | ongoing
2025-01-09 | T Levels | e meeting John Herring Director of Organisational Development and Culture GM NW NHS | met to discuss opportunities with T levels as an introcuction into ASC being student ready. Agreed to explore otions and engagement with ASC uptake . Next steps meet with SFC re gudance developmet | Karen | ongoing
2024-10-14 | Student ready | e meeting | Michelle e introduction to discuss the development of a research buddy system for nurses working in social care. Janette is the Assistant Chief Nurse Research & Innovation, and Health & Care Director of the North West Regional Research Delivery Network (RRDN). | Karen
2025-10-10 | Membership | Met Sarah Kennedy Bolton Uni | Learning disabilties Nurse educator to join NW SCNACS | Karen | 2024-10-01
2024-09-24 | Review Date | 1.Need a review date organised for members for next year. | Karen suggested July 2025, to be confirmed | Karen | 2025-07-31
2024-09-24 | National Priorities - Education and Workforce - Being Student Ready | 2.Education of pre-registered nurses. Making the social care sector 'student ready' and building a space to share. Myth busting out on placements and thinking about where the next cohort of students will come from. Social care being a mandatory placement for students. | Sue Noon expressed interest. She has just started welcome packs for students and will share with everyone for them to also pass to other regions. Melanie Stephens and Liz Williams also expressed interest in the chat. | Melanie Stephens / Liz Wiliams/ Sue Noon | ASAP | Student pack, promoted on SCNACS page. KD engaged Dr Nicky Morrell-Scott. KD Meeting arranged 9/1/25 with NHS John Herring Director of Organisational Development and Culture- education workforce developent. KD engaged with or met with: Nursing Workforce Senior Manager . Liz Williams, Melissa Stanton RCN. NHSE / NW ICB CN & Provider DoNs (In person meeting)- colaboration education. Social Care Nursing Workforce & Education Working Group. NW NHSE/ ICB CN Team meeting. Jo Finnerty.
2024-09-24 | Inspiring Module | 4.Melanie uses a module called Inspiring, and has got care home managers to be a part of. Karen mentioned developing sub committees and working groups for this. Putting out a call to arms to plug any gaps. | Melanie has a meeting also regarding this. she invited the group to contact her . | Melanie / Karen | Nov end | Engagement with NW SC nursing workforce education working group. Student pack, promoted on SCNACS page
2024-09-24 | Developing Student Placements - Medical Outreach Programmes | 5.Event coming up where people will share the learning from this | Find out and send the link for this - November 18th. Andrea Boland to be invited (andera.boland@nhs.net) to the meeting to give update on Regional WT&E work and supporting next steps. | Michelle Howarth | Oct end
2024-09-24 | NW Merseyside Examples - Day In the Life Of | 6.With their permission we can use these to reach out to education providers to utilities this with storytelling. Developing communication pieces and flyers for this. | Melanie created a survey and scale for ICB project asking students week by week what they have learnt about themselves. Can we develop this further as data | Sue Noon | Nov End | Promoted on NW SCNACS WWW.
2024-09-24 | Student Experiences | 7.Student experiences - and why they came back to the workplace they had placement at one qualified. | Emily Devitt - From a base level noticed students were not getting external placements and contacted local universities to ask why. Reaching out to those universities. If placements are cancelled within NHS, putting yourself out there so you are contacted. Feedback available also on SCTH website and flyers (lscthub.co.uk) | Emily Devitt | Nov End | KD collected provider examples of blockers for working group discussions.
2024-09-24 | Workshop - Internationally Trained Nurses | 8.To help with transitions. | Get in touch with Mark Brooke or Paula - regulation advisor for NW regarding this. | Mark Brooke/ Karen Davies/All educators | Oct end | KD -Meeting held- no further action required at this time
2024-09-24 | Engaging and Building Relationships with NWAS | 9. More cohesive relationships. Michelle and Karen will feed back. Potential to reduce unnecessary referrals to safeguarding teams. Clinical understanding - how we work and communicate as a profession to reduce misunderstandings on what is reported. Very different safeguarding criteria to social care, Catherine Brierley would be happy to work on NWAS as has been at this for years. Working to improve understanding between professions. | Understanding safeguarding training paramedics get. Where the gaps are we can work towards with them. Emma O'kane has a link to a TED talk on civility and can share this. Melanie said this was an issue with care homes that comes frequently and would like to be involved in this too. Emma to share information with the group . Jacke offered help also with NWAS as had had conversations with them. Emma Okane referenced Angela Clarke re Safe transfers of care - workstream- NWAS involved will provide link ups. Andrea Boland was invited to the next meeting by Jackie Hanson | Karen/Catherine/Emily/ Emma/ Melanie/ Jackie | Ongoing- Acton specific meeting TBA by Oct end | KD Engaged or met with : with NWAS Michelle Ashworth - Angela Clarke- NHS - NWAS partnerships - Emma Orton NWAS - common language - SCNACS re NWAS Janette Dunkerley. NHSE / NW ICB CN & Provider DoNs (In person meeting)- colaboration education. Social Care Nursing Workforce & Education Working Group. NW NHSE/ ICB CN Team meeting(Jackie Hanson). Stu Kaill Senior Programme Development Lead Health inovation Manchester. (SBARD,NEWS2,RESOURCE2). ASC rollout (common language)
2024-09-24 | Paramedic Programme - Edge Hill | 10.The only nurse paramedic programme - to understand concept. Has first cohorts going through. They have invited a student to the January meeting to see what they have learned and their relationship with social care. To explore some challenges that Karen mentioned. Where did they go after the placements. | Put any questions to Karen for the guest speakers in January. | Michelle | Nov end | MH Arranged guest speaker Jan 2025
2024-09-24 | Website Content | 11.Share good stories & best practice so that we can in turn share them on our webpage. Could some of the excellent good practice going on be shared at the start of the next meeting? Can we share this on our website as a knowledge exchange? Sharing good practice through Karen and Michelle - to be shared on Outstanding Society website. Talk about challenges faced and how we will solve these. | Need to tell stories about the residents, experiences of the students, experiences of the care staff, nurse experiences. Invite people who are leading this this area to come and talk about their work to inspire and influence the discussion | All | Ongoing | content shared by KD via OS support,
2024-07-11 | RCN & Activist Academy | RCN are doing work with the Activist Academy. If you want to become more active, please connect with Melissa Stanton |  | All / Melissa Stanton
2024-07-11 | Terms of Reference (ToR) | If no amendments requested, draft ToR will be adopted and uploaded to our webpage. Pay special attention to section 9 - Core Values by Which we Work (or Ways of Working.) If there is anything you would like to add, please let us know. | Suggestions from Michelle 'Being impactful so that its not just a talking shop - what can we take forwards from this meeting?' maybe worded as 'Be honest in your committments'. How we disseminate and act to enable a safe environment that will enable discussion and actions that make a difference to social care nursing. Being solution focused. To make a difference for residents. Regional meeting fights for what is best for our area within the bigger national arena. Commit to actions that are achieveable. | All | 2024-08-16
|  | Confidentiality and information sharing | What is discussed at the meeting may be shared with the nationals SCNACS. This is a safe space so we need to feel comfortable to be able to say, I'm happy to share in this space, but do not want what I am saying to be shared further or referenced in the minutes | All
2024-09-24 | Gaps in Membership | 12. Please come back to Karen or Michelle if you feel there are gaps in your areas / your field / your discipline, and we can discuss those at the next meeting. | Thinking about passionate students who could represent themselves in the sector. Consider who is round the table - who is in the finishing groups and the meetings, identify people to fill the gaps - to be the megaphone for social care users. RCN was coming back with disability members at some point. Sue Noon - has a student in mind. Melanie Stephanie - Recommended Jacob who she will ask. | Sue / Melanie / All | ASAP but before next meeting
2024-07-11 |  | Identifying gaps - if you feel something is missing and if you have contacts who would be keen, passionate and willing to join, please make introductions. | Students are missing, post-reg and pre-reg LD (Learning Disability), MH (Mental Health, Homeless and Public Health. Residents. Admiral Nurses QNI (Queen's Nursing Institute). Prisons. CQC. | All | End July
|  | Barbara has lots of newly qualified and promoted from training - please let her know if you would would like an introduction. |  | Barbara / Karen | If required
|  | Melanie knows some very inspiring LD nurses who are doing amazing, incredible work, as well as nurses in other areas and can make introductions |  | Melanie / Karen | ASAP
2024-07-11 | Preceptorship | Currently trying to implement preceptorship in Cheshire & Merseyside and its proving more difficult than they thought. Happy to feedback more at the next meeting | Could bring Kathy, Designated Social Care Perf(?)
2024-07-11 | Understanding the Pathways and Mechanisms to Support Students to Engage Across a Range of Sectors. | This was a piece of work that Michelle woked on in March 2023 and she will share the report if anyone is interested | Report identiries potential opportunities for streamlining funding. | Michelle
2024-07-11 | Newsletters | If not already signed up, details of how to sign up to the NMC and Skills for Care newsletters are on the Updates and Information tab - but suggestion to submit some guest articles around SCNACs. Paula to put Karen in touch with the NMC Communication Team and perhaps Jez could do the same. | Opportunities to showcase some of the good practice going on in the region / sector and also maybe something around encouraging students to consider the sector as opposed to NHS. | All / Paula / Jez / Karen | As appropriate
2024-07-11 | NMC Support | If there any suggestions or support that people want from the NMC directly, please reach out to Loucia or Paula | If you contact Sonia (Admin.SCNAC@theoutstandingsociety.co.uk), she will be able to put you in touch | All | As required
2024-07-11 | Championing the Sector | Consider who might champion the cause? Suggestions welcome. | We have 2 mayors in the Liverpool and Greater Manchester area - use them to champion the sector and influence what what might be our focus, aims and aspirations for Social Care and Social Care Nurses.
2024-07-11 | Challenge | In the Northwest or in any of the areas would we ever consider adopting a quota style or a commitment to a percentage of hours placement for student nurses in the future? |  | Karen

## Complete
NAME OF GROUP: NORTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-07-23 | NW Wide Learner Webinar: A Future in Social Care Nursing? | Thursday 31 July 2025 11:00am-12:30pm | https://www.tickettailor.com/events/greatermanchestersocialcareacademy/1771448 | Susan Clarke | 2025-07-31 |  | 2025-07-31
2025-07-23 | Action Points Confirmation | Send Action Points of last meeting to new council members and those who confirmed they had not received them |  | Sonia | 2025-07-23 |  | 2025-07-23
2025-07-23 | Social Care National Placement Strategy | Send flyers or links relating to the Skills for Care National Placement Strategy Events to the SCNAC for Distribution |  | Carole | ASAP | These were shared in the chat and can be found on the Updates and Information tab | 2025-07-23
2025-04-03 | Angela Clarke's Commitment | To reply to Karen and link in to Susan and Sue in response to emails. To look up a few things that have been mentioned during the meeting that are quite interesting. |  | Angela Clarke | Before next meeting |  | Advised completed by Adele 23-Jul-25
2025-04-03 | Community of Practice | Formalise the request for networking with other people doing similar work on PSIRF. Could this be an agenda item at the next meeting? | Please email Karen (karen.northwest@scnac.co.uk) and she will liaise with Angela and her team | Angela Clarke | ASAP |  | Advised completed by Adele 23-Jul-25
2024-09-24 | ICB pot of funding | 3.Find out which pot this is so people can reach out. | Liz Williams mentioned Dawn Wearer for funding, and seeing if she can come along next time. Emma OKane will find the email regarding funding she has and share this | Liz Williams/ Emma Okane | ASAP |  | Advised completed by Adele 23-Jul-25
2025-01-08 | RCN Edghill Uni Visit | Melissa will be attending Edghill University on 12Feb25 to discuss Social Care roles and the RCN with student nurse paramedics. | Paula Palmer-Charlery, NMC would love to hear an update following this visit. | Melissa Stanton | 2025-02-12 |  | 2025-02-12
2025-01-08 | Next Quarter North West SCNAC Meeting | The next meeting date is TBC, but will be in April 2025. If there are any events or conferences in April that might affect attendance, please let us know (Admin.SCNAC@theoutstandingsociety.co.uk) and we will do our best to avoid these dates. | SEE UPDATE FOR CONFIRMED MEETING DATE | All / Sonia | ASAP | Meeting date has been confirmed as Thursday 3rd April 2025 at 11.30am. | 2025-02-10
2025-01-08 | SCNACs Update Meeting - Friday 17th January 2025 from 14:30-15:30 | Book your free place now at this meeting | https://www.eventbrite.co.uk/e/social-care-nursing-advisory-councils-where-are-we-now-tickets-1113668224639?aff=oddtdtcreator | SCNACs | 2025-01-17 |  | 2025-01-17
2025-01-08 | Slides from January Meeting | Share the slides with all Council members |  | Sonia | ASAP | Slides distributed with the attendance and action points log | 2025-02-10
2025-01-08 | Skills for Care Update | Prepare and share a slide with the national skills for care activity updates to circulate with the meeting notes. |  | Lindsey Dawson | Included with meeting follow up |  | 2025-01-15
2024-09-24 | NHS England Representation | Update Jackie Hanson's Organisation to 'Northwest NHS / NHS Englan |  | Alan | ASAP
2024-07-11 | Local Priorities | What should our local priorities be? Please submit your ideas | We will organise a poll with all of the ideas | All | 31-Jul-24 to be agreed at the next meeting | Adoped local priorities are: 1) Developing relationships for admissions avoidance 2) Ensuring social care is 'student nurse ready' | 2024-09-24
2024-07-11 | Claire Pryor's new post | Can we invite her to a future meeting | Claire is starting her new post at Salford on 31st July as the first chair in Social Care | Karen / Michelle |  | Claire will attend to monthly SCNACs meetings in order to feedback to all Chairs/Co-chairs in all regions. | 2024-07-31
2024-07-11 | Terms of Reference (ToR) | NMC is missing from the membership | See update |  |  | 12Jul24 - NMC not being listed was a complete oversight and has been updated on all regional ToR. | 2024-07-12

## Updates and Information
NAME OF GROUP: NORTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-07-23 | FoNS Maria and Mohammad Talk About Resilience-Based Clinical Supervision | Was going to be shared in the meeting by Karen, but we ran out of time! | https://www.fons.org/news/maria-and-mohammad-talk-about-rbcs/ |  | For Reference
2025-07-23 | Skills for Care: Social Care as a Nursing Placement of Choice: Connecting locally to meet the recommendations of the strategy webinar | Wednesday 10 September 2025, 13:00-15:00 | https://www.skillsforcare.org.uk/news-and-events/Events/September/Social-Care-as-a-Nursing-Placement-of-Choice.aspx | Skills for Care | 2025-09-10
2025-07-23 | Skills for Care: Delegated healthcare in action: Local voices, shared solutions - face to face event | Tuesday 30 September 2025, 10:00-16:00, North West Warrington | https://events.skillsforcare.org.uk/skillsforcare/frontend/reg/tRegisterEmailNew.csp?pageID=703610&eventID=2177&tempPersonID=466621 | Skills for Care | 2025-09-30
2025-07-23 | Skills for Care: Social Care as a Nursing Placement of Choice: Embedding the strategy - face to face event | Tuesday 11 November 2025, 09:30-15:30 | https://www.skillsforcare.org.uk/news-and-events/Events/November/Social-Care-as-a-Nursing-Placement-of-Choice.aspx | Skills for Care | 2025-11-11
2025-07-23 | Skills for Care: Preceptorship Resources | Shared in the chat | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Preceptorship.aspx | Skills for Care | For Reference
2025-07-23 | International round table event on person centred approaches | Event to take place 27th November | This will be online and chaired by Lucy Gillespie. The panel members (there are 4) will be asked a series of questions and they will be audiance participation. There will be an infographic produced at the end. | Michelle Howarth | 2025-02-26
2025-07-23 | Guide to implementing indirect practice supervision and assessment in Greater Manchester | Shared in the chat - this is the guide that Sarah Kennedy produced as part of the project looking into indirect practice supervision and assessment | https://gmipsa.co.uk/ | Sarah Kennedy | For Reference
2025-07-23 | Big Knowledge in Small Doses | Shared in the chat - Falls Prevention and Frailty | https://hub.gmintegratedcare.org.uk/asc/wp-content/uploads/sites/11/2025/04/Wider-Workforce-Falls-Prevention-and-Frailty.pdf | Marie Lovell | For Reference
2025-07-23 | Finding a Light in Dementia Training | Shared in the chat by Susan Clarke for format ideas | https://hub.gmintegratedcare.org.uk/social-care-academy/finding-a-light-in-dementia-training/ |  | For Reference
2025-04-17 | NIHR Social Care Nursing Opportunities | NIHR have asked us to share the aside opportunities. Please do share these with your networks: | https://www.nihr.ac.uk/researcher-development-programme-social-care-nurses | NIHR | For Reference
2025-04-03 | RBCS for Social Care - Foundation of Nursing Studies | Shared in the chat - Free to access for all Adult Social Care Nurses | https://www.fons.org/programmes-development-opportunities/clinical-supervision/rbcs-for-social-care/#:~:text=We%20are%20delighted%20to%20be%20able%20to%20offer,England%2C%20the%20programme%20is%20offered%20free%20of%20charge. | Karen Davies | For Reference
2025-04-03 | T Level Placements | Webinar around hosting T level placements. It’s Thursday 10th April 1-1.45pm. more info here. | https://url.uk.m.mimecastprotect.com/s/M_H_Cy8LoTmYAxLhZfnUxQpzZ?domain=tickettailor.com | Karen Davies | For Reference
2025-04-03 | T Level Stakeholder Network | There’s a T level stakeholder network which will be sharing regular updates. If you would like to be added to the distribution list, please contact nhsgm.gm.workforce@nhs.net. Also, the head of workforce development shares her insights into the impact of T levels: | https://url.uk.m.mimecastprotect.com/s/D9_CCzmMvtNKO54TXhBU90EFc?domain=gatsby.org.uk | Karen Davies | For Reference
2025-04-03 | Social Care CLE Guide | Shared in the chat | https://www.gmcle.co.uk | Susan Clarke | For Reference
2025-04-03 | Perceptions in BJN | Recent research Susan and Sue have published with Chester Uni | Can be accessed from the BJN by searching 'Perceptions of social care: Sue Clarke, Sue Noon, Kate H Knight and Jonathan Hay' - Its the comments section on page 314 vol 34 | Susan Clarke | For Reference
2025-04-03 | Research and Education Opportunities and Grants | Publicised via Greater Manchester Social Care Provider Network and other key groups | https://hub.gmintegratedcare.org.uk/asc/news-events/ | Susan Clarke | For Reference
2025-01-17 | SCNAC Progress and Impact 6 months on | If you were not able to make our virtual progress meeting in January, you can listen again here: | https://www.youtube.com/watch?v=7qa5APv9BIw&t=3s | SCNACs | For Reference
2025-01-08 | NMC - Useful Information for Prescribers | Shared in the chat: Relates to Px rights as a RN or RM also working as a PA or AA | https://www.nmc.org.uk/standards/standards-for-post-registration/standards-for-prescribers/useful-information-for-prescribers/?utm_source=Nursing%20and%20Midwifery%20Council&utm_medium=email&utm_campaign=14795113_20241210-%20prescribers%20update%20in%20PA%20and%20AA%20Roles&dm_t=0,0,0,0,0 | Paula Palmer- Charlery | For Reference
2025-01-08 | RCN North West Independent Health and Social Care Face to Face Event | Date: 23Apr25 in Saint Helens. | Further details to follow but in the meantime, contact Melissa Stanton (melissa.stanton@rcn.org.uk)
2024-09-24 | Cheshire & Merseyside Digital Newsletter for Student Placement Providers in the Social Care Sector | Newsletter forwarded by Sue Noon was attached to the email with the meeting action points. |  |  | For Reference
2024-09-24 | Funding to Support Nursing Apprenticeships 2024/2025 | The deadline for the funding Emma O'Kane had information on was Midday on Friday 31st May 2024 BUT contact included to point people in the right direction for further information of what is available. | Please contact Dawn.Werra@nhs.net if you would like support from the Social Care Training hub to enrol onto the apprenticeships mentioned in the funding guidelines. https://forms.office.com/pages/responsepage.aspx?id=slTDN7CF9UeyIge0jXdO48s8d514ZUVLkY3r8-squIJUODM4N1BMMUdKVDNQTzc4UkdNT1pGRkRGRSQlQCN0PWcu |  | For Reference
2024-09-24 | TED Talk on Civility | Shared in the chat by Emma O'Kane | When rudeness in teams turns deadly ¦ Chris Turner ¦ TEDxExeter - YouTube |  | For Reference
2024-09-24 | Lancashire and South Cumbria - Social Care Placements | Shared in the chat by Liz Williams | Social Care Placements – Lancashire and South Cumbria Training Hub (lscthub.co.uk) |  | For Reference
2024-09-24 | IPE Student Training Care Homes | Shared in the chat by Melanie Stephens | IPE Student Training Care Homes: A Longitudinal Study - Centre for Applied Health Research (salford.ac.uk) |  | For Reference
2024-09-24 | SCNACs Celebration Key Note Speaker | Major General Tim Hodgetts was the Key Note Speaker at our SCNACs celebration on 12th September | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ |  | For Reference
2024-07-11 | North West Region SCNAC Page | For Reference | https://theoutstandingsociety.co.uk/north-west-region/ |  | For Reference
2024-07-11 | NMC - Review of Nursing and Midwifery Practice Learning | In January 2024 we announced that we would be commissioning researching to nursing and midwifery students’ practice learning requirements. If you’d like to keep up to date and be notified of future opportunities to get involved, please sign up to our community of interest. | https://r1.dotdigital-pages.com/p/129A-1B4W/practicelearning |  | For Reference
2024-07-11 | NMC - Council Governance | Members can request to observe a meeting (if they haven't already) to learn more about the NMC and also try to influence & raise the social care voice: | https://www.nmc.org.uk/about-us/governance/the-council/council-governance/ |  | For Reference
2024-07-11 | Principles of Preceptorship | Preceptorship is the structured start for newly registered nurses, midwives and nursing associates. See link for useful resources from the NMC. | https://www.nmc.org.uk/standards/guidance/preceptorship/ |  | For Reference
2024-07-11 | Funding | Shared in the chat by Barbara: Just a reminder of the RNDA for LD and top up from NA and AP (general and mental health) funding currently with ICB's. £8800 pa per student. |  |  | For Reference
2024-07-11 | NMC Newsletter | NMC Newsletters: You can sign up to receive any number of regular newsletters. Please note that our email newsletters may go into your ‘junk’ folder so I’d advise you save ‘info@nmc-news.org.uk’ to your safe senders list. | https://www.nmc.org.uk/news/email-newsletters/ |  | For Reference
2024-07-11 | Skills for Care Newsletter | If you aren't already signed up, you can sign up for the Skills for Care newsletter using the following link: | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Join-the-nursing-community.aspx |  | For Reference
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' | For Reference | https://vimeo.com/958966378?share=copy |  | For Reference |  | 2024-06-19