## OPEN
NAME OF GROUP: SOUTH EAST Region SCNAC (Social Care Nursing Advisory Councils) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-16 | Gaps in the Council | Please let us know if you think there are gaps in the Council. If you have suggestions of people to fill the gaps, please make introductions. | Invite paramedics from SE, Acute Emergency and Safeguarding Leads - all with a view to reducing hospital admissions. Need frontline nurses from all six ICBs in SE Region | All / Sue | Before next Meeting - Apr25
2025-01-16 | Council Membership - Adult Social Care Nurses | Write a one-page document detailing the desired nurse representatives from all ICBS and send it to Sue from SESCA and Ryan from RCN for distribution. | (Cross section - Care home / LD / Nursing education - all from Adult Social Care - Nurse leaders of the future) - Sue from SESCA to make introductions | Zoe / Scarlett
2025-01-16 | Clinical Competencies Framework | Share the clinical competancies framework with the group for feedback and review |  | Scarlett | See FoNS link on Updates and Information Tab |  | 2025-01-28
2025-01-16 | What is Adult Social Care | Zoe and Scarlett are leading on one of the primary care education sessions in Sussex to present on 'What is Social Care' Will document so this can be replicated and rolled out |  | Zoe / Scarlett | 2025-01-30
2025-01-16 | Nurses Day Event | Set up a splinter group to work on video clips and other collaborative activities for International Nurses Day |  | Zoe / Scarlett
2025-01-16 | Brighton Pride | Set up a splinter group to organize participation in Brighton Pride, including inviting Duncan and Deborah | Brighton Pride dates are 02-03Aug25 | Zoe / Scarlett
2025-01-16 | Data Collection and Analysis | Firm down the definitive metrics for data collection on hospital admissions and safeguarding trends with Andrea. Andrea to think about who we could link with to report on this? | Add as a standing agenda item: What is going on in our areas? Trends on admissions? What are safeguarding scenes that are coming up? What are the top 3 priorities across health and social care? | Zoe / Scarlett / Andrea
2025-01-16 | Student Nurse Engagement | Collaborate with Sharon to incorporate social care into sessions with nursing students to raise the profile of social care careers |  | Marissa
2025-01-16 | Insurance Issues in Social Care | Write up the process of overcoming insurance issues for advanced nursing care in social care settings and share it with the group. | Also liaise with Nuno and Louise in the London region SCNAC as this was discussed in their quarterly meeting too. | Scarlett
2025-01-16 | Research Work | Arrange for an update on the research work being done in collaboration with Bucks New Uni and RSG re developing advances practice - a grant supported by Burdett |  | Rachael Corser | For next meeting
2024-09-26 | Council Members Bios and Photos | Please submit your high resolution photos and short bios (approx. 100 words) to Sonia (Admin.SCNAC@theoutstandingsociety.co.uk) to be included on the website | Some Bios and Photos are still outstanding | All | ASAP | Ongoing
2024-09-26 | Task and Finish Groups for Local Priorities: 1) Clinical Competencies 2) Communications Plan | To hold 4 meetings of an hour for each group, before next quarterly meeting - 16Jan25 with clear outcomes. | - Dates to go out for these. - Volunteers to contact Zoe and Scarlett for each repsective group (Zoe, Comms plan and Scarlett, Clinical Competencies). - Melanie to sit in on task and finish group. - How to expand to social care nurses for parity and inclusiveness. - Victoria wants to be involved in clinical competency group. - Marianne - Locality manager will sit in on clinical competency - either Mike Bailey (Sussex) or Rachel Reid (Barkshire). - Members do not have to sit on the council, if you know of people who can add value to these task and finish groups please introduce them to the chairs. | Zoe / Scarlett | 2025-01-10 | See attached ToR and Membership details
2024-09-26 | Chief Nurse Awards for Adult Social Care | Identify colleagues to nominate to recognise their work in the sector | Open to all in the sector, not just nurses. Team awards also available. https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms
2024-07-02 | Regional Organisations and Signposting | Identify regional organisations and how we link in to them - information on the webpage | Use webpage as a central repository to share information within ICBs / within the region (care associations, NIHR, access to research, access to training resources, access to funding, groups) For NHS colleagues - is Social Care represented on the meetings you are going to? | All | Ongoing | Zoe sent email to all council members with a table to complete details of regional organisations to include on the webpage. Wants to move forward with this, section on website. Members still to complete ahead of comms meeting - ongoing work
2024-07-02 | Data | Look at safeguarding issues. | Is there a way to look at data for the South East and look at what the themes are around safeguarding and clinical competencies? Any suggestions welcome | Zoe / Scarlett / Andrea / All | Ongoing | Had a discussion with Andrea - looking at data and safeguarding issues. Looking at a later point. Revisited with Andrea 25/10/24. Andrea will look at any trends
2024-07-02 | Social Media | Develop a social media platform | People tend to interact with social media more frequently than visiting a website, so if we use social media to signpost to the webpage, it might get more traction (there is already an original ICB page so could re-visit and develop) | SCNAC Team | Ongoing | Within next 3 months - social media platform for South East region This will form part of the Comms plan

## Complete
NAME OF GROUP: SOUTH EAST Region SCNAC (Social Care Nursing Advisory Council) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-02 | Gaps in the Council | Please let us know if you think there are gaps in the Council. If you have suggestions of people to fill the gaps, please make introductions. | Gaps for Student nurses and Nursing Associates Suggestion to approach SESCA - South East Social Care Association (https://sesca.org.uk) Healthwatch (very proactive in Sussex) Grassroot nursing voice (West Sussex MAR project or comparible projects across the SE) | All | Review 16-Jan-25 | Scarlett - managed to cover mental health nurses and student nurses following Kent meeting. Healthwatch currently identifying a representative. jo.tuck@healthwatchwestsussex.co.uk www.healthwatch.co.uk Review members of council in January - do we have frontline and care workers representing us? Replaced with updated action point from 16Jan25 meeting 16Jan25 invite paramedics from SE, Acute Emergency and Safeguarding Leads - all with a view to reducing hospital admissions. Need frontline nurses from all six ICBs in SE Region
2024-09-26 | Suggested Task and Finish Group Actions | Clinical competencies, training framework and resources, assessment and validating procedures for skillset, timeline for implementation plan, competency framework. Not as many volunteers for communication plan group. Marianne on behalf of skills for care. Conversations with NMC. Kate Meacock happy to be involved in communication. | Ideas put forward below Sharon Lee - Wound care, EOL care, long term conditions. Masline - Development programme and competencies. Sharon - Newsletters for nurses and colleagues on ground. Walter - Avenues for feedback, surveys, Q&A's. Kate - Identifying good local organisations. Signposting where residents and families can go. Marianne - Use communication opportunities for Deborah to take information to Steven Kinnock. Showcasing best practice. Zoe - Directory on website for regions. Looking at learning hubs to support effective outcomes. Complex care training in nursing homes, disability sites and out in the community. | Zoe / Scarlett | ASAP | Incorporated in the ToR | 2024-10-01
2024-09-26 | Terms of Reference (ToR) for Task and Finish Groups | Send out draft ToR |  | Zoe/Scarlett | ASAP | Distributed to members with dates | 2024-10-01
2024-07-02 | Communications Map | How do we make sure that the message is getting out to all organisations - large and small | Making sure there is not too much communication. Ensure all messages are saying the same thing. | Zoe |  | Ongoing - part of the task and finish group. Considering people in their homes with complex needs. Outline and promote individually not just as a whole. In NHS lots of departments, same definitions needed in Social care. Not just defining, but for schools and universities. Patricia happy to help and Jo can support in wider communications. Encourage people to engage in local healthwatch team. | 2024-10-01
2024-07-02 | Terms of Reference (ToR) | If no amendments requested, draft ToR will be adopted and uploaded to our webpage |  | All | 2024-08-16 | ToR available on the SE webpage
2024-07-02 | Regional Priorities | Consider everything discussed to day. Chair and Co-Chair to meet with Regional CNO to see what would be realistic in the SE area. | If you have any further thoughts on regional priorities, please come back with your suggestions within 2 weeks. | All Zoe / Scarlett / Andrea | 14-Aug-24 Before next meeting | Available on the website
2024-07-02 | NMC thoughts on regional priorities | Zoe to meet with David outside of meeting to hear his thoughts on which priorities we should be looking at |  | Zoe / David | 2024-08-31

## Updates and Information
NAME OF GROUP: SOUTH EAST Region SCNAC (Social Care Nursing Advisory Council) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-16 | SCNAC Email Address update | New email addresses for Zoe and Scarlett | Zoe: zoe.southeast@scnac.co.uk Scarlet: scarlett.southeast@scnac.co.uk |  | For Reference
2025-01-16 | Brighton and Hove Pride | Date is 02/03Aug25 | https://www.brighton-pride.org |  | For Reference
2025-01-16 | FoNS Resilience-Based Clinical Supervision | Request for link to be shared. RBCS is a free programme so Deborah Sturdy recommends it is shared far and wide. | https://www.fons.org/programmes-development-opportunities/clinical-supervision/ |  | For Reference
2025-01-16 | NIHR Research Programme for Social Care (RPSC) | Shared in the chat | https://www.nihr.ac.uk/research-funding/funding-programmes/research-programme-for-social-care |  | For Reference
2025-01-16 | VIVALDI Social Care | Shared in the chat | https://theoutstandingsociety.co.uk/vivaldi-social-care/ https://vimeo.com/920041294 | The OS | for Reference
2025-01-16 | The Patient/Service User Journey | Slide shared by Sharon Lee in the chat and attached to the meeting follow up email sent on ***** |  |  | for Reference
2024-09-26 | SCNACs Celebration Event - 12Sep24 | Shared in the chat | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ |  | For Reference
2024-09-26 | Social Care Nurses Critical - NT Article | Shared in the chat | https://www.nursingtimes.net/news/social-care/social-care-nurses-critical-to-incoming-healthcare-overhaul-12-09-2024/ |  | For Reference
2024-09-26 | Chief Nurse Adult Social Care Awards | Deborah Sturdy is keen to award as many as possible so please do nominate your excellent colleagues - not just nurses, can be all staff. | Criteria: https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms/chief-nurse-adult-social-care-awards-nomination-criteria Nomination Form: https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms |  | Ongoing
2024-09-26 | Primary Care & General Practice Nursing Career & Core Capabilities Framework - Skills for Health | Shared in the chat - Link to the first wave of GPN ones that was published yesterday A foreword by National Deputy Director, Paul Vaughan | https://www.skillsforhealth.org.uk/article/a-foreword-by-national-deputy-director-paul-vaughan-primary-care-general-practice-nursing-career-core-capabilities-framework/ |  | For Reference
2024-07-02 | South East Region SCNAC Page | For reference | https://theoutstandingsociety.co.uk/scnac-south-east-region/
2024-07-02 | National Priorities | Voted in by all SCNACs regions: 1. Eduation and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference
2024-07-02 | Skills for Care Nursing | From Chat - Skills for Care, new website pages for nursing | https://www.skillsforcare.org.uk/Regulated-professions/Nursing/Nursing.aspx
2024-06-19 | Link for Virtual Meeting 'Introducting the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy |  |  |  | 2024-06-19

## Future
NAME OF GROUP: SOUTH EAST Region SCNAC (Social Care Nursing Advisory Councils) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-07-02 | Focus Group for people supported by social care | Consider focus group for people that are supported by social care? | In Kent there are some projects to upskill social care nurses - for example tissue viability. Sharon Lee in Kent and Medway ICB is a good person to speak to | Suggestion by Joanna Grant |  | Will come at a later stage
2024-07-02 | Relatives and people who use services | Consider should we have our SCNACs page as an information portal for relatives and people who use services as well? | So that people can see the expanse of health and social care working toether |  |  | Review at a later stage
2024-07-02 | Social Care Structure | Social Care NEEDS structure (NHS banding) - Take this thought to Deborah Sturdy to see if this is something that can be linked in to national strategy |  | Zoe | When appropriate