## OPEN
NAME OF GROUP: SOUTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Action Log - OPEN
Meeting date / date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-23 | Non-Medical Prescribing Working Group | Please email Emily if interested in joining the non-medical prescribing working group. | emily.southwest@scnac.co.uk | All | ASAP - If interested
2025-01-23 | Learning Disability and Autism Focus | Discuss the possibility of including a learning disability and autism priority either within the Southwest SCNAC or another region as this is not covered. | Emily to bring this to the monthly SCNACs meeting. | Emily / SCNACs / The OS | Will report back at the next Meeting
2025-01-23 | LeDeR Governance Group Participation | Regarding LD & Autism focus - Coordinate with Denise to identify a representative from the Southwest SCNAC to join the LeDeR Governance Group. | Denise to mention SCNACs in the Governance meeting w/c27Jan25 and contact Sonia following the meeting (Admin.SCNAC@theoutstandingsociety.co.uk) | Denise / Sonia | Following Governance Meeting | 30-Jan-25 The BNSSG LeDeR governance group were delighted that the SCNACs were keen to join. Please can you let Sonia know it you would be happy to represent SCNACs at this group.
2025-01-23 | Council Members Bios | Submit a short bio (100 words) and photo for the website. | https://theoutstandingsociety.co.uk/scnac-south-west-region/ | All | 2025-02-28
2025-01-23 | Sharing Presentation Slides | Send presentation slides to Sonia for dissemination with the meeting summary notes. | Admin.SCNAC@theoutstandingsociety.co.uk | Presenters | ASAP
23-Jan-25 24-Sep-24 | Project Repository Submissions | Submit innovative project details to Emily or Sonia for inclusion in the Southwest SCNAC project repository which is shared on the SW webpage. | https://theoutstandingsociety.co.uk/scnac-south-west-region/ Include brief description of project, links, logo and contact details | All | Ongoing | 10Jan25 Currently have x 2 projects listed on repository: - Dorset Hydration Project - Resilience Based Clinical Supervision The following is due to be added by the OS: - Dental pain in Care Homes - Advanced Diploma -ASC Nursing
2025-01-23 | Regional Priority - Communications Plan, partnering with South East SCNAC | If anyone is interested in being involved, please email Scarlett MacDonald, Co-Chair for the South East SCNAC - scarlett.southeast@scnac.co.uk |  | All | ASAP - If interested
2025-01-23 | Regional Priority - Support and Access to Nurse Prescribing in Social Care | If anyone is interested in being involved, please email Emily Pimm, Co-Chair for the South West SCNAC - emily.southwest@scnac.co.uk | Would be particularly interested in introductions to community pharmacists or similar - they don't have to be on the council to join the working group and they don't have to be in the South West either. If anyone has any recommendations for someone to make a difference with this priority, please make contact. | All | ASAP - If interested
2025-01-23 | New Co-Chair | Deborah Sturdy is interviewing three candidates for the position of Co-Chair for the South West and we will update the council once she has made her decision and look forward to making introductions at the next meeting. |  | Deborah Sturdy | 2025-01-29
2025-01-23 | Regional Priorities | An link to all of the regional priorities being covered by SCNACs across England is attached and if anyone has interest/passion/extensive knowledge for any of these priorities, they would be welcome to be introduced to the working groups, even if out of region. | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-regional-priorities-released/ | All | ASAP - If interested | Some of the priorities have been updated since they were first released. The East of England second priority is 'Medication Sustainability' and the most up to date priorities are listed against each regional page: https://theoutstandingsociety.co.uk/scnac/
2024-09-24 | Small leaflet - SCNACS | Suggestion from Ashleigh Fox who has been hearing recently about how effective old-fashioned 'snail mail' is. Could we design/develop a small leaflet on SCNACs to be posted with NMC/RCN post directly to our Social Care Nurses who aren't on socials? Even if it's a WhatsApp community to join? |  |  |  | 21Oct24 Add this to partnership working/ comms plan working group
2024-09-24 | SW SCNAC Infographic | Suggestion (Teresa Chinn) to put something together to explain what we are after and a rough format | Make is super easy for people to share |  |  | 21Oct24 Add this to partnership working/ comms plan working group
2024-09-24 | Quarterly Meeting Invites | Will get feedback for next meeting |  | Emily |  | SCNAC admin arranging invitations to quarterly meetings
2024-09-24 | Working Group - Safer Recruitment | Workforce planning and recruitment. If you have a passion for/experience to share best practice and knowledge across councils and departments of Health and Social Care | Jill - mentioned Skills for Care did lots of safer recruitment, and took a lot from Safeguarding children - knows lots of resources. Dedrey - Happy to help on workforce planning - experience with Skills for Care. Charlotte - Could do a best practice document to link. Shelagh - a potential speaker an happy to field members of her team into the relevant working groups. | Jill, Dedrey, Charlotte, Shelagh |  | 21Oct24 Postpone until further notice
2024-09-24 | Access and support to Nurse Prescribing in ASC | Setting up objectives, timescales to report back. | Volunteers: Tersea, Esther, Leanne, Margot, Vicky, Jodie, Glos ICB rep (Jane Haros) | Emily |  | 10Jan25 Working group has been established and a first meeting planned for 15Jan25 where we will be confirming TOR for the group, outlining project aims and plans and getting a research and development update from Prof. Claire Pryor. Membership list and agenda for meeting has been sent to members. Will update council on next regional meeting on 23Jan25.
2024-09-24 | Working Group - Partnership Working | Setting up objectives, timescales to report back. Streamlining and building relationships - what impact has it made. Person centred. | Volunteers: Simon, Margot, Ashleigh, Shelagh, Jill (Skills for Care priority), Paula, Leanne, Jane to nominate a team member, Vicky, Teresa really interested to join and has a colleague who may be interested, Charlotte will ask Ambulance rep, Dedrey has a collaborative sector group so may help, Esther has hospice contacts. |  |  | SW have now joined SE SCNAC Communications Plan group to share work. Emails sent to the people who volunteered to take part in working group with invite to SE working group. Emily is arranging a meeting with Co-Chairs of South East to get an update on this priority before next council meeting.
2024-06-25 | Members photo and bio on website | All members to provide a high resolution photo and short bio to be uploaded to the South West page | Send to Admin.SCNAC@theoutstandingsociety.co.uk Please can you put SOUTH WEST SCNAC in the subject line. | All / The OS | 2024-08-31 | Council members reminded at Sept meeting 10Jan25 Currently 5 council member bios on website (one to update - AF) Co-chair will request for more bios to be sent in next meeting on 23Jan25. | Ongoing
2024-09-24 | Membership Gaps | Looking for representation from Cornwall. Also looking for representative nurse associate, early careers nurse, internationally educated nurse, student nurse and representatives from universities of an HEI | If you have any suggestions to cover these areas, please make introductions with them to Charlotte (chair.southwest@scnac.co.uk) and Emily (co-chair.southwest@scnac.co.uk) Suggestion from Hilary: LARCH - Listening and Reaching out to Care Homes within Somerset | All | ASAP | 10Jan25 Work continues to ensure the councils reflective of the social care nursing workforce. New member recruited Jan25 (BM - Mental Health RN) | Ongoing
2024-06-25 | Would we consider? | A Team Leader who would like to go on the Nurse Associate Course but not there yet | Invite as a guest to one of the next meetings | Jackie | When appropriate | 10Jan25 Request update from Jackie at next council meeting.
2024-06-25 | Advanced Diploma in Adult Social Care Nursing | If anyone is interested please contact Margo Whitaker | Margo has been developing this advanced diploma with and accredited by Botton University. Starting in August and open to all SW Nurses | Margot Whitaker | August 2024 | 10Jan25 Margot has sent information and awaiting for this to be uploaded to project repository (website currently being re-developed).
2024-06-25 | Advanced Practice | Is carried out through the apprenticeship scheme and is accessible. | For more information on Brunel Care's journey on this please contact Theresa - teresa.chinn@brunelcare.org.uk | Theresa / All | As required | 10Jan25 This information to be sent out to council members in next meeting's minutes. | 2025-01-23
2024-06-25 | Dental Pain Study | Pat to share the study she has just finished | If interested in seeing the results of the study please email patricia.schofield@plymouth.ac.uk | Pat | When possible | 10Jan25 Information sent to OS and awaiting for it to be added to project repository.
2024-06-25 | Professional Practice Newsletter for Nurses working across all ICS Settings. | Stu's team are in the process of setting up a professional practice newsletter | Celebrating and promoting innovative projects / stories / opportunities and roles so we can learn and celebrate with each other | Stu | To share with council if possible. | 10Jan25 This information would be great to share with London 'raising the profile of ASC nursing' regional priority - to discuss at next council meeting and then share in minutes with members of SW SCNAC. | 2025-01-23

## Complete
NAME OF GROUP: SOUTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Action Log - COMPLETED
Meeting date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2024-09-24 | Membership Gaps |  | Gaps remaining - BSW and Cornwall Areas | All | Ongoing | 10/1/25 - Membership updated with participants from BSW and Cornwall area. | 2025-01-10
2024-09-24 | Skills for Care: Adult Workforce Strategy | Recent launch - aligning with this workforce strategy. | Developed a template which Jill can share. Recommendations and commitments. Webinars coming up. Jill to send presentation/template over | Jill |  | Skills for Care Workforce Strategy: https://www.skillsforcare.org.uk/Workforce-Strategy/Home.aspx | 2024-10-01
2024-09-24 | Sarah Merritt's last meeting | Finishing with NHS Devon at the end of October | Remove from the membership | Sonia | 2024-10-31 | Member list updated. | 2024-09-24
2024-06-25 | Social Media Platform | Could we have a linked in page or X page - further discussions required | Charlotte to meet with Teresa to see how they can work together and anyone else is welcome to join. | Charlotte / Teresa |  | Become part of partnership working and communications plan priority | 2024-09-24
2024-06-25 | Innovation | If you are doing anything innovational in your care settings and you fancy writing a blog or a summary of any work that you're doing really well, or about being on the council - please do! | Share with Charlotte, Emily or Sonia and we can arrange to add it to the website. Looking to evidence with projects. Templates, social media campaign. Any ideas on themes. Could look at prevention/innovation | All | Ongoing | Has become innovation and improvement evidenced by project repository | 2024-09-24
2024-06-25 | Best Practise Ideas | Submit best practise ideas to be shared on the South West web page. |  | All | Ongoing - When relevant | Project repository reminded members at Sept meeting | 2024-09-24
2024-09-24 | Membership Gaps | If you think we are missing a person or organisation from the council, please let us know. |  | All | Ongoing | Representation from Ambulance Service - Charlotte sorted. Have welcomed several members since June. | 2024-08-01
2024-06-25 | SWAST | Invite SWAST (South West Ambulance Service Trust) to join council |  |  | ASAP | 26Jul24 Charlotte has emailed a contact from SWAST with ToR and waiting for them to get back with a name. Now have SWAFT rep on council | 2024-08-01
2024-06-25 | Regional CNO Network Meeting | Charlotte to attend and will feedback any relevant information. If anyone has any questions that Charlotte can take to the table please send her a message. |  | Charlotte | End July - with feedback at next meeting | SCNAC is now part of this network, we will aim to have a SCNAC representative at each meeting | 2024-08-01
2024-06-25 | Draft Terms of Reference (ToR) | Unless any feedback is received, the Draft ToR will be adopted and added to the website |  | The OS | 2024-08-30 | Comments: add NMC to all ToR - Actioned for all regions now published on SW webpage | 2024-08-31
2024-06-25 | Consider Ambulance Trusts | They are the transistion between Social Care and the Acute Trusts |  | SCNACs |  | Rep on council | 2024-08-01
2024-06-24 | NMC | NMC have regular newsletters - please do sign up. | Links shared in the chat can be found in the 'Updates and Information' tab. To sign up to NMC newsletters you can click here: https://www.nmc.org.uk/news/email-newsletters/ | All |  | Sent with June meeting agenda, invited NMC to add to partnership organisations list | 2024-09-01
2024-06-25 | Local Priorities | Will collate the ideas given in the chat, during and received after the meeting and send out in a poll to the council. | If anyone that wasn't able to attend has any suggestions or anyone that did and thought about it more after the meeting finished, please send your ideas in to be added to the poll. Not too big and very specific. | Charlotte / Sonia | 2024-08-31 | Discussed and confirmed at June meeting 1. Innovation and improvement (project repository) 2. Partnership working | 2024-09-01

## Updates and Information
NAME OF GROUP: SOUTH WEST Region Social Care Nursing Advisory Councils (SCNACs) Updates and Information
Date | Subject | Action | Details | Lead | Due Date | Update | Date Completed
2025-01-30 | Skills for Care South West Regional Event 'Leading social care now and in the future - Attract and retain, train and transform' on 6th March 2025 from 10am-3pm | Shared by Jill Croskell Please sign up to our FREE Southwest regional event with lunch and refreshments on the 6th of March- 10am to 3pm at the Albemarle Centre, Taunton, Somerset TA1 1BA. An opportunity to engage with your Peer group across the Southwest region, led by speakers with direct experience, providing an opportunity to ask your questions to our panel. I look forward to seeing you there – All welcome! All best wishes, Jill. | Facilitated and funded by Skills for Care, this is your event, your fraternity.. we need your transparent narrative..and we need to be solution focussed. We will also have a provider podcast (employer enabled) giving you the opportunity to record your own Podcast during the day or later date. Bookings for this FREE event have just been opened: https://www.skillsforcare.org.uk/news-and-events/Events/March/Leading-social-care-now-and-in-the-future-Attract-and-retain-train-and-transform.aspx Easy access from Train Station and Car Park and fully enabled building access. | Jill Croskell | 2025-03-06
2025-01-23 | Chair/Co-Chair Role | The division of Chair and Co-Chair within SCNACs has been taken away and for each region we now have joint Co-Chairs. Charlotte Fry has stepped down from her Co-Chair position due to work commitments, but still very much wants to remain on the council and contribute when she can, for which we are very grateful. |  |  | For Reference
2025-01-23 | RCN Nursing Across Independent Health and Social Care | Shared in chat | https://www.rcn.org.uk/employment-and-pay/nursing-across-social-care-and-independent-health-services#s=8&c=1&q=&r=UK%20wide&t=8dd7c5b2-e8c3-4b31-9772-28db8b4e0c2f&p=&a=tabNational&sr=0 | Sarah Winfield- Davies | For Reference
2025-01-23 | FoNS - Clinical Supervision | Shared in chat | https://www.fons.org/programmes-development-opportunities/clinical-supervision/ |  | For Reference
2025-01-23 | Southern Healthcare Central Hub - Diploma | Shared in the chat and attached to the email with the meeting follow up sent on **** | https://southernhealthcare-my.sharepoint.com/:f:/g/personal/shc-central-hub_southernhealthcare_co_uk/EioGOl6cyapCnIQZQEYTQk8Bpkzs0R9gW7mgPhValAObmw?e=OGBWXy | Margot Whittaker | For Reference
2024-09-24 | Chief Nurse Adult Social Care Awards | Nomination criteria | https://www.gov.uk/government/publications/chief-nurse-adult-social-care-awards-nomination-forms/chief-nurse-adult-social-care-awards-nomination-criteria |  | For Reference
2024-09-24 | SCNACs Celebration Event | Shared in chat | https://theoutstandingsociety.co.uk/social-care-nursing-advisory-councils-inaugural-event-marks-a-milestone-for-the-sector/ |  | For Reference
2024-09-24 | Skills for Care | Online webinar | Skills for care have got an online webinar | Leanne Vinakadina
2024-09-24 | Special Interests | Teresa Chinn - Falls prevention, Social media and advanced practice in ASC Esther Mackillican - Dementia, frailty, EOL care Sarah Saunders - EOL care, advance care planning, wound/pressure ulcer prevention Leanne Vinakadina - Dementia and complex health conditions Jakki Whitehead - Dementia, EOL, frailty, mental health and complexity. Specialist practitioners working as a clinician/trainer within a nursing home.
2024-09-24 | Academy of Fabulous Stuff | Shared in chat | https://fabnhsstuff.net/ Fab NHS Stufffabnhsstuff.net
2024-06-25 | South West Region SCNAC Page | For Reference and includes the adopted ToR | https://theoutstandingsociety.co.uk/scnac-south-west-region/
2024-06-25 | National Priorities | Voted in by all SCNACs regions: 1. Education and Training (including access to) 2. Workforce Planning and Develpment | For reference | All | For Reference
2024-06-25 | Skills for Care | Social Care Provider settings have the opportunity to sign up for the Adult Social Care Workforce Data set. Providing they do that to a certain level, they are able to access funding towards training (previously it would have been the workforce Development fund. Going forward will be through the training and development fund, distributed by the NHS Business Services Authority. Currently on hold due to the election but information included for reference and for website. | https://www.skillsforcare.org.uk/Funding/Workforce-Development-Fund/Changes-to-funding-for-learning-and-development-for-adult-social-care.aspx
2024-06-25 | Resilience Based Clinical Supervision through FoNS | For information - free of charge | https://www.fons.org/programmes-development-opportunities/clinical-supervision/rbcs-for-social-care/
2024-06-25 | Global Network for Long Term Care | Shared in chat
2024-06-25 | NMC Advanced Practice | On 27Mar24 our Council approved our recommendation that we develop a combination of approaches to the regulation of advanced practice. Please join our community of interest for all the latest updates, including opportunities to get involved. | https://www.nmc.org.uk/about-us/our-role/advanced-practice-review/ To stay updated about the NMC Review of practice learning you can sign up here: https://r1.dotdigital-pages.com/p/129A-1B4W/practicelearning
2024-06-19 | Link for Virtual Meeting 'Introducing the Chairs and Co-Chairs' |  | https://vimeo.com/958966378?share=copy |  |  |  | 2024-06-19